## Projects
ProjectID | ProductName | DepartmentID | ProjectManagerID | Project_Country | City | Project_Country_Latitude | Project_Country_Longitude | PlannedStartDate | PlannedEndDate | ActualStartDate | ActualEndDate | Status | PlannedBudget (EUR) | ActualBudget (EUR) | RiskLevel | CompletionPercentage | Country_Flag
P001 | InstantPay | D07 | E087 | #VALUE! | Porto | 41.1654 | -8.6409 | 01/08/2025 | 13/03/2026 | 26/08/2025 |  | In Progress | 351000 | 219000 | Medium | 67 | #VALUE!
P002 | EuroWallet | D04 | E118 | #VALUE! | Limerick | 52.6816 | -8.6271 | 30/12/2024 | 29/09/2025 | 20/12/2024 | 08/09/2025 | Completed | 1379000 | 1534000 | Low | 100 | #VALUE!
P003 | OpenBank API | D04 | E004 | #VALUE! | Aalborg | 57.037 | 9.921 | 27/07/2024 | 07/03/2025 | 13/08/2024 | 04/03/2025 | Completed | 2180000 | 2218000 | Low | 100 | #VALUE!
P004 | Tap-to-Pay POS | D03 | E029 | #VALUE! | Seville | 37.408 | -5.965 | 28/11/2024 | 26/08/2025 | 10/12/2024 | 12/09/2025 | Completed | 921000 | 958000 | Low | 100 | #VALUE!
P005 | BNPL Flex | D01 | E089 | #VALUE! | Limerick | 52.6597 | -8.6393 | 22/08/2025 | 08/01/2026 | 08/09/2025 |  | In Progress | 1437000 | 361000 | Medium | 25 | #VALUE!
P006 | SEPA Plus | D05 | E061 | #VALUE! | Debrecen | 47.5342 | 21.6376 | 16/02/2025 | 25/06/2025 | 04/03/2025 |  | In Progress | 1349000 | 1308000 | High | 91 | #VALUE!
P007 | FX Hedge | D01 | E011 | #VALUE! | Liège | 50.6151 | 5.586 | 22/06/2024 | 04/04/2025 | 30/06/2024 | 23/04/2025 | Completed | 1250000 | 1281000 | Low | 100 | #VALUE!
P008 | Merchant Insights | D04 | E046 | #VALUE! | Esbjerg | 55.4649 | 8.4702 | 17/07/2025 | 30/01/2026 | 07/08/2025 |  | In Progress | 1179000 | 537000 | High | 47 | #VALUE!
P009 | RiskGuard | D03 | E029 | #VALUE! | Bruges | 51.2288 | 3.2408 | 18/01/2025 | 23/08/2025 | 09/02/2025 |  | In Progress | 2775000 | 1170000 | Medium | 42 | #VALUE!
P010 | KYC Express | D06 | E080 | #VALUE! | Prague | 50.064 | 14.4335 | 19/03/2025 | 18/07/2025 | 15/03/2025 |  | In Progress | 2767000 | 798000 | High | 28 | #VALUE!
P011 | Fraud Shield | D05 | E049 | #VALUE! | Valencia | 39.4864 | -0.36581 | 26/02/2025 | 01/10/2025 | 21/02/2025 |  | In Progress | 1925000 | 546000 | Medium | 31 | #VALUE!
P012 | Payout Hub | D06 | E073 | #VALUE! | Rotterdam | 51.9389 | 4.4804 | 03/08/2025 | 23/04/2026 | 19/08/2025 |  | In Progress | 508000 | 466000 | Low | 83 | #VALUE!
P013 | Card Tokenization | D05 | E045 | #VALUE! | Rotterdam | 51.9189 | 4.4898 | 28/10/2024 | 30/04/2025 | 15/12/2024 |  | Delayed | 2328000 | 1479000 | High | 56 | #VALUE!
P014 | PayLink | D07 | E049 | #VALUE! | Coimbra | 40.2164 | -8.4189 | 23/06/2025 | 11/11/2025 | 24/06/2025 |  | In Progress | 1437000 | 1042000 | Medium | 74 | #VALUE!
P015 | PISP Gateway | D04 | E087 | #VALUE! | Esbjerg | 55.4714 | 8.4743 | 16/06/2025 | 17/11/2025 | 07/07/2025 |  | In Progress | 576000 | 457000 | Low | 75 | #VALUE!
P016 | AISP DataVault | D07 | E029 | #VALUE! | Wroclaw | 51.1163 | 17.0446 | 16/08/2025 | 26/05/2026 | 03/09/2025 |  | In Progress | 2164000 | 746000 | High | 32 | #VALUE!
P017 | InvoiceNow | D05 | E046 | #VALUE! | Marseille | 43.2956 | 5.3548 | 29/09/2024 | 14/02/2025 | 10/10/2024 |  | Delayed | 1185000 | 1153000 | High | 80 | #VALUE!
P018 | Digital IBAN | D07 | E029 | #VALUE! | Poznan | 52.4217 | 16.9274 | 25/05/2025 | 22/01/2026 | 21/06/2025 |  | In Progress | 651000 | 503000 | Medium | 75 | #VALUE!
P019 | SoftPOS | D02 | E118 | #VALUE! | Ghent | 51.0527 | 3.7248 | 09/04/2024 | 02/12/2024 | 10/04/2024 | 23/11/2024 | Completed | 475000 | 498000 | Low | 100 | #VALUE!
P020 | SplitPay | D07 | E048 | #VALUE! | Ghent | 51.0711 | 3.7134 | 14/03/2026 | 23/12/2026 |  |  | Not Started | 2006000 | 0 | Medium | 0 | #VALUE!
P021 | Recurring Billing | D02 | E009 | #VALUE! | Marseille | 43.2918 | 5.3806 | 26/02/2025 | 31/07/2025 | 25/03/2025 |  | In Progress | 413000 | 367000 | Medium | 87 | #VALUE!
P022 | PayID | D02 | E004 | #VALUE! | Iași | 47.1575 | 27.6162 | 13/07/2025 | 24/12/2025 | 14/07/2025 |  | In Progress | 2573000 | 614000 | Medium | 21 | #VALUE!
P023 | Loyalty Engine | D05 | E011 | #VALUE! | Budapest | 47.5029 | 19.0469 | 28/04/2025 | 09/10/2025 | 22/04/2025 |  | In Progress | 322000 | 183000 | Low | 53 | #VALUE!
P024 | Chargeback Manager | D02 | E048 | #VALUE! | Naples | 40.8538 | 14.2815 | 26/11/2024 | 18/07/2025 | 19/01/2025 |  | Delayed | 931000 | 606000 | High | 61 | #VALUE!
P025 | InstantPay | D02 | E087 | #VALUE! | Porto | 41.148 | -8.6281 | 28/01/2025 | 01/12/2025 | 28/01/2025 |  | In Progress | 240000 | 121000 | Medium | 50 | #VALUE!
P026 | EuroWallet | D02 | E080 | #VALUE! | Salzburg | 47.8166 | 13.0603 | 01/05/2024 | 07/12/2024 | 06/06/2024 |  | Delayed | 890000 | 724000 | Medium | 75 | #VALUE!
P027 | OpenBank API | D05 | E004 | #VALUE! | Patras | 38.2536 | 21.7404 | 10/03/2025 | 20/11/2025 | 17/03/2025 |  | In Progress | 2732000 | 2391000 | Medium | 92 | #VALUE!
P028 | Tap-to-Pay POS | D06 | E004 | #VALUE! | Bruges | 51.1982 | 3.2137 | 31/03/2025 | 15/09/2025 | 14/04/2025 |  | In Progress | 1791000 | 1123000 | Low | 64 | #VALUE!
P029 | BNPL Flex | D02 | E087 | #VALUE! | Coimbra | 40.1873 | -8.4085 | 26/07/2025 | 20/04/2026 | 07/08/2025 |  | In Progress | 2151000 | 711000 | Medium | 32 | #VALUE!
P030 | SEPA Plus | D06 | E008 | #VALUE! | Krakow | 50.0785 | 19.934 | 25/07/2025 | 16/01/2026 | 31/07/2025 |  | In Progress | 454000 | 157000 | Medium | 38 | #VALUE!
P031 | FX Hedge | D02 | E004 | #VALUE! | Athens | 37.9718 | 23.7462 | 12/01/2026 | 12/08/2026 |  |  | Not Started | 1558000 | 0 | Low | 0 | #VALUE!
P032 | Merchant Insights | D06 | E029 | #VALUE! | Brussels | 50.835 | 4.3625 | 09/05/2025 | 14/01/2026 | 04/05/2025 |  | In Progress | 2279000 | 702000 | High | 28 | #VALUE!
P033 | RiskGuard | D07 | E069 | #VALUE! | Espoo | 60.2012 | 24.6713 | 14/08/2025 | 28/01/2026 | 31/08/2025 |  | In Progress | 1475000 | 1355000 | High | 92 | #VALUE!
P034 | KYC Express | D07 | E046 | #VALUE! | Linköping | 58.4289 | 15.6225 | 20/01/2025 | 06/10/2025 | 27/01/2025 |  | In Progress | 2640000 | 705000 | High | 25 | #VALUE!
P035 | Fraud Shield | D06 | E042 | #VALUE! | Valencia | 39.4659 | -0.38445 | 25/06/2025 | 26/01/2026 | 25/06/2025 |  | In Progress | 1154000 | 317000 | High | 25 | #VALUE!
P036 | Payout Hub | D03 | E029 | #VALUE! | Aarhus | 56.1827 | 10.1845 | 04/06/2024 | 09/01/2025 | 31/07/2024 |  | Delayed | 1233000 | 827000 | High | 61 | #VALUE!
P037 | Card Tokenization | D05 | E029 | #VALUE! | Krakow | 50.0712 | 19.9473 | 26/12/2025 | 29/09/2026 |  |  | Not Started | 520000 | 0 | Medium | 0 | #VALUE!
P038 | PayLink | D06 | E004 | #VALUE! | Seville | 37.3723 | -5.9707 | 21/05/2025 | 17/10/2025 | 19/05/2025 |  | In Progress | 2710000 | 777000 | Medium | 30 | #VALUE!
P039 | PISP Gateway | D04 | E029 | #VALUE! | Barcelona | 41.366 | 2.1748 | 16/03/2025 | 10/09/2025 | 25/03/2025 |  | In Progress | 703000 | 341000 | Low | 49 | #VALUE!
P040 | AISP DataVault | D05 | E069 | #VALUE! | Seville | 37.3977 | -5.9877 | 11/04/2025 | 04/10/2025 | 28/04/2025 |  | In Progress | 1455000 | 559000 | Low | 39 | #VALUE!
P041 | InvoiceNow | D01 | E069 | #VALUE! | Bucharest | 44.4206 | 26.1006 | 02/08/2025 | 02/12/2025 | 15/08/2025 |  | In Progress | 1945000 | 560000 | Medium | 30 | #VALUE!
P042 | Digital IBAN | D03 | E029 | #VALUE! | Utrecht | 52.0869 | 5.1345 | 15/09/2024 | 31/05/2025 | 19/09/2024 | 27/06/2025 | Completed | 1411000 | 1500000 | Low | 100 | #VALUE!
P043 | SoftPOS | D06 | E046 | #VALUE! | Timișoara | 45.7556 | 21.2021 | 19/02/2026 | 22/06/2026 |  |  | Not Started | 2958000 | 0 | Medium | 0 | #VALUE!
P044 | SplitPay | D04 | E072 | #VALUE! | Patras | 38.2587 | 21.7493 | 07/01/2025 | 23/10/2025 | 26/01/2025 |  | In Progress | 392000 | 377000 | Medium | 85 | #VALUE!
P045 | Recurring Billing | D01 | E061 | #VALUE! | Malmö | 55.6006 | 13.0096 | 21/06/2024 | 03/01/2025 | 07/08/2024 |  | Delayed | 1569000 | 1126000 | High | 64 | #VALUE!
P046 | PayID | D06 | E073 | #VALUE! | Odense | 55.399 | 10.3901 | 05/01/2025 | 25/09/2025 | 13/01/2025 |  | In Progress | 424000 | 196000 | High | 46 | #VALUE!
P047 | Loyalty Engine | D01 | E061 | #VALUE! | Rome | 41.8929 | 12.4963 | 19/05/2024 | 16/12/2024 | 02/06/2024 | 30/12/2024 | Completed | 814000 | 743000 | Medium | 100 | #VALUE!
P048 | Chargeback Manager | D03 | E029 | #VALUE! | Salzburg | 47.7952 | 13.0369 | 08/07/2025 | 18/01/2026 | 21/07/2025 |  | In Progress | 1431000 | 1345000 | Medium | 88 | #VALUE!
P049 | InstantPay | D02 | E038 | #VALUE! | Antwerp | 51.2169 | 4.4165 | 11/05/2025 | 01/12/2025 | 13/05/2025 |  | In Progress | 2500000 | 502000 | Medium | 22 | #VALUE!
P050 | EuroWallet | D06 | E100 | #VALUE! | Cork | 51.8838 | -8.4749 | 09/11/2024 | 08/04/2025 | 05/11/2024 | 19/04/2025 | Completed | 354000 | 351000 | Low | 100 | #VALUE!
P051 | OpenBank API | D07 | E073 | #VALUE! | Eindhoven | 51.4469 | 5.4733 | 27/07/2025 | 30/05/2026 | 28/07/2025 |  | In Progress | 2674000 | 723000 | Medium | 25 | #VALUE!
P052 | Tap-to-Pay POS | D07 | E073 | #VALUE! | Ostrava | 49.823 | 18.2727 | 06/02/2025 | 19/07/2025 | 17/02/2025 |  | In Progress | 1516000 | 1065000 | Medium | 63 | #VALUE!
P053 | BNPL Flex | D03 | E029 | #VALUE! | Salzburg | 47.79 | 13.0676 | 03/06/2025 | 10/11/2025 | 12/06/2025 |  | In Progress | 2669000 | 793000 | Medium | 32 | #VALUE!
P054 | SEPA Plus | D04 | E077 | #VALUE! | Munich | 48.1527 | 11.5628 | 27/03/2024 | 12/08/2024 | 27/03/2024 |  | Delayed | 450000 | 332000 | High | 58 | #VALUE!
P055 | FX Hedge | D02 | E046 | #VALUE! | Gothenburg | 57.6905 | 11.9877 | 07/05/2024 | 07/10/2024 | 12/05/2024 |  | Delayed | 1064000 | 511000 | High | 47 | #VALUE!
P056 | Merchant Insights | D03 | E029 | #VALUE! | Constanța | 44.1705 | 28.6489 | 07/01/2025 | 07/05/2025 | 22/01/2025 |  | In Progress | 204000 | 182000 | Medium | 90 | #VALUE!
P057 | RiskGuard | D06 | E038 | #VALUE! | Hamburg | 53.5319 | 9.974 | 31/01/2025 | 08/06/2025 | 15/02/2025 |  | In Progress | 2936000 | 1458000 | Low | 51 | #VALUE!
P058 | KYC Express | D06 | E118 | #VALUE! | Lyon | 45.7533 | 4.8455 | 27/12/2025 | 25/07/2026 |  |  | Not Started | 2574000 | 0 | Low | 0 | #VALUE!
P059 | Fraud Shield | D02 | E010 | #VALUE! | Aarhus | 56.1609 | 10.1939 | 06/05/2025 | 18/12/2025 | 02/06/2025 |  | In Progress | 222000 | 56000 | Medium | 22 | #VALUE!
P060 | Payout Hub | D06 | E011 | #VALUE! | Antwerp | 51.2058 | 4.4115 | 06/07/2025 | 16/05/2026 | 04/07/2025 |  | In Progress | 2619000 | 1863000 | Medium | 64 | #VALUE!
P061 | Card Tokenization | D02 | E012 | #VALUE! | Aalborg | 57.031 | 9.9185 | 18/09/2025 | 08/04/2026 | 18/10/2025 |  | In Progress | 685000 | 446000 | Low | 62 | #VALUE!
P062 | PayLink | D01 | E069 | #VALUE! | Turku | 60.4489 | 22.2563 | 17/07/2025 | 09/05/2026 | 11/08/2025 |  | In Progress | 1138000 | 547000 | Medium | 43 | #VALUE!
P063 | PISP Gateway | D07 | E118 | #VALUE! | Cork | 51.8985 | -8.4645 | 03/11/2025 | 21/06/2026 |  |  | Not Started | 981000 | 0 | Low | 0 | #VALUE!
P064 | AISP DataVault | D06 | E077 | #VALUE! | Timișoara | 45.7506 | 21.1948 | 04/05/2024 | 06/09/2024 | 10/05/2024 |  | Delayed | 1820000 | 1230000 | High | 59 | #VALUE!
P065 | InvoiceNow | D03 | E029 | #VALUE! | Liège | 50.6215 | 5.5668 | 15/04/2025 | 09/11/2025 | 27/04/2025 |  | In Progress | 1736000 | 878000 | Medium | 54 | #VALUE!
P066 | Digital IBAN | D07 | E069 | #VALUE! | Constanța | 44.1502 | 28.6288 | 09/02/2024 | 11/07/2024 | 09/02/2024 | 25/07/2024 | Completed | 1974000 | 2204000 | Medium | 100 | #VALUE!
P067 | SoftPOS | D05 | E118 | #VALUE! | Paris | 48.8749 | 2.3442 | 30/08/2025 | 20/01/2026 | 11/09/2025 |  | In Progress | 2141000 | 1625000 | Low | 71 | #VALUE!
P068 | SplitPay | D04 | E100 | #VALUE! | Brno | 49.1938 | 16.6246 | 10/12/2025 | 07/06/2026 |  |  | Not Started | 379000 | 0 | Medium | 0 | #VALUE!
P069 | Recurring Billing | D04 | E069 | #VALUE! | Lille | 50.6197 | 3.0674 | 23/04/2024 | 24/01/2025 | 27/04/2024 | 25/02/2025 | Completed | 1786000 | 1817000 | Low | 100 | #VALUE!
P070 | PayID | D07 | E118 | #VALUE! | Graz | 47.0595 | 15.457 | 02/04/2024 | 09/11/2024 | 09/05/2024 |  | Delayed | 1479000 | 1340000 | Medium | 73 | #VALUE!
P071 | Loyalty Engine | D02 | E038 | #VALUE! | Berlin | 52.5141 | 13.4094 | 07/03/2026 | 23/08/2026 |  |  | Not Started | 2454000 | 0 | Medium | 0 | #VALUE!
P072 | Chargeback Manager | D05 | E061 | #VALUE! | Miskolc | 48.1182 | 20.7844 | 16/08/2025 | 18/03/2026 | 11/08/2025 |  | In Progress | 1162000 | 1038000 | High | 91 | #VALUE!

## Milestones
MilestoneID | ProjectID | MilestoneName | PlannedCompletionDate | ActualCompletionDate | Status
M0001 | P001 | Requirements & Scoping | 26/09/2025 | 04/10/2025 | Completed
M0002 | P001 | MVP Ready | 21/11/2025 |  | On Track
M0003 | P001 | Regulatory Approval | 16/01/2026 |  | On Track
M0004 | P001 | General Availability | 13/03/2026 |  | On Track
M0005 | P002 | Requirements & Scoping | 08/03/2025 | 09/03/2025 | Completed
M0006 | P002 | MVP Ready | 15/05/2025 | 25/05/2025 | Completed
M0007 | P002 | Regulatory Approval | 22/07/2025 | 07/08/2025 | Completed
M0008 | P002 | General Availability | 29/09/2025 | 03/09/2025 | Completed
M0009 | P003 | Requirements & Scoping | 20/09/2024 | 16/09/2024 | Completed
M0010 | P003 | MVP Ready | 15/11/2024 | 25/11/2024 | Completed
M0011 | P003 | Regulatory Approval | 10/01/2025 | 30/01/2025 | Completed
M0012 | P003 | General Availability | 07/03/2025 | 27/02/2025 | Completed
M0013 | P004 | Requirements & Scoping | 03/02/2025 | 01/02/2025 | Completed
M0014 | P004 | MVP Ready | 12/04/2025 | 06/04/2025 | Completed
M0015 | P004 | Regulatory Approval | 19/06/2025 | 24/06/2025 | Completed
M0016 | P004 | General Availability | 26/08/2025 | 29/08/2025 | Completed
M0017 | P005 | Requirements & Scoping | 25/09/2025 | 02/10/2025 | Completed
M0018 | P005 | MVP Ready | 30/10/2025 |  | On Track
M0019 | P005 | Regulatory Approval | 04/12/2025 |  | On Track
M0020 | P005 | General Availability | 08/01/2026 |  | On Track
M0021 | P006 | Requirements & Scoping | 20/03/2025 | 19/03/2025 | Completed
M0022 | P006 | MVP Ready | 21/04/2025 | 16/04/2025 | Completed
M0023 | P006 | Regulatory Approval | 23/05/2025 |  | Delayed
M0024 | P006 | General Availability | 25/06/2025 |  | Delayed
M0025 | P007 | Requirements & Scoping | 01/09/2024 | 21/09/2024 | Completed
M0026 | P007 | MVP Ready | 12/11/2024 | 25/11/2024 | Completed
M0027 | P007 | Regulatory Approval | 22/01/2025 | 08/02/2025 | Completed
M0028 | P007 | General Availability | 04/04/2025 | 09/04/2025 | Completed
M0029 | P008 | Requirements & Scoping | 04/09/2025 | 02/09/2025 | Completed
M0030 | P008 | MVP Ready | 23/10/2025 |  | On Track
M0031 | P008 | Regulatory Approval | 11/12/2025 |  | On Track
M0032 | P008 | General Availability | 30/01/2026 |  | On Track
M0033 | P009 | Requirements & Scoping | 13/03/2025 | 14/03/2025 | Completed
M0034 | P009 | MVP Ready | 06/05/2025 | 15/05/2025 | Completed
M0035 | P009 | Regulatory Approval | 29/06/2025 |  | Delayed
M0036 | P009 | General Availability | 23/08/2025 |  | On Track
M0037 | P010 | Requirements & Scoping | 18/04/2025 | 15/04/2025 | Completed
M0038 | P010 | MVP Ready | 18/05/2025 | 24/05/2025 | Completed
M0039 | P010 | Regulatory Approval | 17/06/2025 |  | On Track
M0040 | P010 | General Availability | 18/07/2025 |  | On Track
M0041 | P011 | Requirements & Scoping | 21/04/2025 | 30/04/2025 | Completed
M0042 | P011 | MVP Ready | 14/06/2025 | 14/06/2025 | Completed
M0043 | P011 | Regulatory Approval | 07/08/2025 |  | On Track
M0044 | P011 | General Availability | 01/10/2025 |  | Delayed
M0045 | P012 | Requirements & Scoping | 07/10/2025 | 05/10/2025 | Completed
M0046 | P012 | MVP Ready | 12/12/2025 |  | On Track
M0047 | P012 | Regulatory Approval | 16/02/2026 |  | On Track
M0048 | P012 | General Availability | 23/04/2026 |  | On Track
M0049 | P013 | Requirements & Scoping | 13/12/2024 | 01/01/2025 | Completed
M0050 | P013 | MVP Ready | 28/01/2025 |  | Delayed
M0051 | P013 | Regulatory Approval | 15/03/2025 | 06/04/2025 | Completed
M0052 | P013 | General Availability | 30/04/2025 | 21/05/2025 | Completed
M0053 | P014 | Requirements & Scoping | 28/07/2025 | 29/07/2025 | Completed
M0054 | P014 | MVP Ready | 01/09/2025 | 07/09/2025 | Completed
M0055 | P014 | Regulatory Approval | 06/10/2025 |  | Delayed
M0056 | P014 | General Availability | 11/11/2025 |  | On Track
M0057 | P015 | Requirements & Scoping | 24/07/2025 | 27/07/2025 | Completed
M0058 | P015 | MVP Ready | 01/09/2025 | 02/09/2025 | Completed
M0059 | P015 | Regulatory Approval | 09/10/2025 |  | Delayed
M0060 | P015 | General Availability | 17/11/2025 |  | On Track
M0061 | P016 | Requirements & Scoping | 25/10/2025 |  | On Track
M0062 | P016 | MVP Ready | 04/01/2026 |  | On Track
M0063 | P016 | Regulatory Approval | 16/03/2026 |  | On Track
M0064 | P016 | General Availability | 26/05/2026 |  | On Track
M0065 | P017 | Requirements & Scoping | 02/11/2024 |  | Delayed
M0066 | P017 | MVP Ready | 07/12/2024 |  | Delayed
M0067 | P017 | Regulatory Approval | 10/01/2025 |  | Delayed
M0068 | P017 | General Availability | 14/02/2025 |  | Delayed
M0069 | P018 | Requirements & Scoping | 24/07/2025 | 31/07/2025 | Completed
M0070 | P018 | MVP Ready | 23/09/2025 | 22/09/2025 | Completed
M0071 | P018 | Regulatory Approval | 22/11/2025 |  | On Track
M0072 | P018 | General Availability | 22/01/2026 |  | On Track
M0073 | P019 | Requirements & Scoping | 07/06/2024 | 18/06/2024 | Completed
M0074 | P019 | MVP Ready | 05/08/2024 | 06/08/2024 | Completed
M0075 | P019 | Regulatory Approval | 03/10/2024 | 04/10/2024 | Completed
M0076 | P019 | General Availability | 02/12/2024 | 22/11/2024 | Completed
M0077 | P020 | Requirements & Scoping | 24/05/2026 |  | On Track
M0078 | P020 | MVP Ready | 03/08/2026 |  | On Track
M0079 | P020 | Regulatory Approval | 13/10/2026 |  | On Track
M0080 | P020 | General Availability | 23/12/2026 |  | On Track
M0081 | P021 | Requirements & Scoping | 05/04/2025 | 09/04/2025 | Completed
M0082 | P021 | MVP Ready | 14/05/2025 | 20/05/2025 | Completed
M0083 | P021 | Regulatory Approval | 22/06/2025 |  | Delayed
M0084 | P021 | General Availability | 31/07/2025 |  | On Track
M0085 | P022 | Requirements & Scoping | 23/08/2025 | 26/08/2025 | Completed
M0086 | P022 | MVP Ready | 03/10/2025 | 30/09/2025 | Completed
M0087 | P022 | Regulatory Approval | 13/11/2025 |  | On Track
M0088 | P022 | General Availability | 24/12/2025 |  | On Track
M0089 | P023 | Requirements & Scoping | 08/06/2025 | 12/06/2025 | Completed
M0090 | P023 | MVP Ready | 19/07/2025 | 14/07/2025 | Completed
M0091 | P023 | Regulatory Approval | 29/08/2025 |  | On Track
M0092 | P023 | General Availability | 09/10/2025 |  | On Track
M0093 | P024 | Requirements & Scoping | 23/01/2025 | 02/02/2025 | Completed
M0094 | P024 | MVP Ready | 23/03/2025 |  | Delayed
M0095 | P024 | Regulatory Approval | 20/05/2025 |  | Delayed
M0096 | P024 | General Availability | 18/07/2025 |  | Delayed
M0097 | P025 | Requirements & Scoping | 14/04/2025 | 12/04/2025 | Completed
M0098 | P025 | MVP Ready | 30/06/2025 | 29/06/2025 | Completed
M0099 | P025 | Regulatory Approval | 15/09/2025 |  | Delayed
M0100 | P025 | General Availability | 01/12/2025 |  | On Track
M0101 | P026 | Requirements & Scoping | 25/06/2024 | 16/07/2024 | Completed
M0102 | P026 | MVP Ready | 19/08/2024 | 10/09/2024 | Completed
M0103 | P026 | Regulatory Approval | 13/10/2024 | 29/10/2024 | Completed
M0104 | P026 | General Availability | 07/12/2024 | 30/12/2024 | Completed
M0105 | P027 | Requirements & Scoping | 12/05/2025 | 12/05/2025 | Completed
M0106 | P027 | MVP Ready | 15/07/2025 | 16/07/2025 | Completed
M0107 | P027 | Regulatory Approval | 17/09/2025 |  | Delayed
M0108 | P027 | General Availability | 20/11/2025 |  | On Track
M0109 | P028 | Requirements & Scoping | 12/05/2025 | 08/05/2025 | Completed
M0110 | P028 | MVP Ready | 23/06/2025 | 28/06/2025 | Completed
M0111 | P028 | Regulatory Approval | 04/08/2025 |  | On Track
M0112 | P028 | General Availability | 15/09/2025 |  | On Track
M0113 | P029 | Requirements & Scoping | 01/10/2025 | 30/09/2025 | Completed
M0114 | P029 | MVP Ready | 07/12/2025 |  | On Track
M0115 | P029 | Regulatory Approval | 12/02/2026 |  | On Track
M0116 | P029 | General Availability | 20/04/2026 |  | On Track
M0117 | P030 | Requirements & Scoping | 06/09/2025 | 11/09/2025 | Completed
M0118 | P030 | MVP Ready | 20/10/2025 | 24/10/2025 | Completed
M0119 | P030 | Regulatory Approval | 03/12/2025 |  | On Track
M0120 | P030 | General Availability | 16/01/2026 |  | On Track
M0121 | P031 | Requirements & Scoping | 06/03/2026 |  | On Track
M0122 | P031 | MVP Ready | 28/04/2026 |  | On Track
M0123 | P031 | Regulatory Approval | 20/06/2026 |  | On Track
M0124 | P031 | General Availability | 12/08/2026 |  | On Track
M0125 | P032 | Requirements & Scoping | 10/07/2025 | 14/07/2025 | Completed
M0126 | P032 | MVP Ready | 11/09/2025 | 07/09/2025 | Completed
M0127 | P032 | Regulatory Approval | 12/11/2025 |  | On Track
M0128 | P032 | General Availability | 14/01/2026 |  | On Track
M0129 | P033 | Requirements & Scoping | 24/09/2025 | 29/09/2025 | Completed
M0130 | P033 | MVP Ready | 05/11/2025 |  | On Track
M0131 | P033 | Regulatory Approval | 17/12/2025 |  | On Track
M0132 | P033 | General Availability | 28/01/2026 |  | On Track
M0133 | P034 | Requirements & Scoping | 25/03/2025 | 26/03/2025 | Completed
M0134 | P034 | MVP Ready | 29/05/2025 | 02/06/2025 | Completed
M0135 | P034 | Regulatory Approval | 02/08/2025 |  | On Track
M0136 | P034 | General Availability | 06/10/2025 |  | On Track
M0137 | P035 | Requirements & Scoping | 17/08/2025 | 15/08/2025 | Completed
M0138 | P035 | MVP Ready | 10/10/2025 | 16/10/2025 | Completed
M0139 | P035 | Regulatory Approval | 03/12/2025 |  | On Track
M0140 | P035 | General Availability | 26/01/2026 |  | On Track
M0141 | P036 | Requirements & Scoping | 28/07/2024 | 02/08/2024 | Completed
M0142 | P036 | MVP Ready | 21/09/2024 |  | Delayed
M0143 | P036 | Regulatory Approval | 15/11/2024 |  | Delayed
M0144 | P036 | General Availability | 09/01/2025 |  | Delayed
M0145 | P037 | Requirements & Scoping | 05/03/2026 |  | On Track
M0146 | P037 | MVP Ready | 13/05/2026 |  | On Track
M0147 | P037 | Regulatory Approval | 21/07/2026 |  | On Track
M0148 | P037 | General Availability | 29/09/2026 |  | On Track
M0149 | P038 | Requirements & Scoping | 27/06/2025 | 04/07/2025 | Completed
M0150 | P038 | MVP Ready | 03/08/2025 | 02/08/2025 | Completed
M0151 | P038 | Regulatory Approval | 09/09/2025 |  | On Track
M0152 | P038 | General Availability | 17/10/2025 |  | On Track
M0153 | P039 | Requirements & Scoping | 29/04/2025 | 04/05/2025 | Completed
M0154 | P039 | MVP Ready | 13/06/2025 | 19/06/2025 | Completed
M0155 | P039 | Regulatory Approval | 27/07/2025 |  | On Track
M0156 | P039 | General Availability | 10/09/2025 |  | Delayed
M0157 | P040 | Requirements & Scoping | 25/05/2025 | 27/05/2025 | Completed
M0158 | P040 | MVP Ready | 08/07/2025 | 17/07/2025 | Completed
M0159 | P040 | Regulatory Approval | 21/08/2025 |  | On Track
M0160 | P040 | General Availability | 04/10/2025 |  | Delayed
M0161 | P041 | Requirements & Scoping | 01/09/2025 | 31/08/2025 | Completed
M0162 | P041 | MVP Ready | 02/10/2025 | 02/10/2025 | Completed
M0163 | P041 | Regulatory Approval | 01/11/2025 |  | On Track
M0164 | P041 | General Availability | 02/12/2025 |  | On Track
M0165 | P042 | Requirements & Scoping | 18/11/2024 | 20/11/2024 | Completed
M0166 | P042 | MVP Ready | 22/01/2025 | 06/02/2025 | Completed
M0167 | P042 | Regulatory Approval | 27/03/2025 | 24/03/2025 | Completed
M0168 | P042 | General Availability | 31/05/2025 | 09/06/2025 | Completed
M0169 | P043 | Requirements & Scoping | 21/03/2026 |  | On Track
M0170 | P043 | MVP Ready | 21/04/2026 |  | On Track
M0171 | P043 | Regulatory Approval | 22/05/2026 |  | On Track
M0172 | P043 | General Availability | 22/06/2026 |  | On Track
M0173 | P044 | Requirements & Scoping | 20/03/2025 | 19/03/2025 | Completed
M0174 | P044 | MVP Ready | 31/05/2025 | 04/06/2025 | Completed
M0175 | P044 | Regulatory Approval | 11/08/2025 |  | Delayed
M0176 | P044 | General Availability | 23/10/2025 |  | On Track
M0177 | P045 | Requirements & Scoping | 09/08/2024 |  | Delayed
M0178 | P045 | MVP Ready | 27/09/2024 | 13/10/2024 | Completed
M0179 | P045 | Regulatory Approval | 15/11/2024 |  | Delayed
M0180 | P045 | General Availability | 03/01/2025 | 27/01/2025 | Completed
M0181 | P046 | Requirements & Scoping | 11/03/2025 | 07/03/2025 | Completed
M0182 | P046 | MVP Ready | 16/05/2025 | 18/05/2025 | Completed
M0183 | P046 | Regulatory Approval | 21/07/2025 |  | On Track
M0184 | P046 | General Availability | 25/09/2025 |  | On Track
M0185 | P047 | Requirements & Scoping | 10/07/2024 | 04/07/2024 | Completed
M0186 | P047 | MVP Ready | 01/09/2024 | 29/08/2024 | Completed
M0187 | P047 | Regulatory Approval | 24/10/2024 | 10/11/2024 | Completed
M0188 | P047 | General Availability | 16/12/2024 | 25/12/2024 | Completed
M0189 | P048 | Requirements & Scoping | 25/08/2025 | 30/08/2025 | Completed
M0190 | P048 | MVP Ready | 13/10/2025 | 19/10/2025 | Completed
M0191 | P048 | Regulatory Approval | 30/11/2025 |  | On Track
M0192 | P048 | General Availability | 18/01/2026 |  | On Track
M0193 | P049 | Requirements & Scoping | 01/07/2025 | 07/07/2025 | Completed
M0194 | P049 | MVP Ready | 21/08/2025 | 18/08/2025 | Completed
M0195 | P049 | Regulatory Approval | 11/10/2025 |  | Delayed
M0196 | P049 | General Availability | 01/12/2025 |  | On Track
M0197 | P050 | Requirements & Scoping | 16/12/2024 | 04/01/2025 | Completed
M0198 | P050 | MVP Ready | 23/01/2025 | 29/01/2025 | Completed
M0199 | P050 | Regulatory Approval | 01/03/2025 | 12/03/2025 | Completed
M0200 | P050 | General Availability | 08/04/2025 | 19/04/2025 | Completed
M0201 | P051 | Requirements & Scoping | 11/10/2025 | 19/10/2025 | Completed
M0202 | P051 | MVP Ready | 27/12/2025 |  | On Track
M0203 | P051 | Regulatory Approval | 14/03/2026 |  | On Track
M0204 | P051 | General Availability | 30/05/2026 |  | On Track
M0205 | P052 | Requirements & Scoping | 18/03/2025 | 16/03/2025 | Completed
M0206 | P052 | MVP Ready | 28/04/2025 | 06/05/2025 | Completed
M0207 | P052 | Regulatory Approval | 08/06/2025 |  | Delayed
M0208 | P052 | General Availability | 19/07/2025 |  | Delayed
M0209 | P053 | Requirements & Scoping | 13/07/2025 | 13/07/2025 | Completed
M0210 | P053 | MVP Ready | 22/08/2025 | 29/08/2025 | Completed
M0211 | P053 | Regulatory Approval | 01/10/2025 |  | On Track
M0212 | P053 | General Availability | 10/11/2025 |  | On Track
M0213 | P054 | Requirements & Scoping | 30/04/2024 |  | Delayed
M0214 | P054 | MVP Ready | 04/06/2024 |  | Delayed
M0215 | P054 | Regulatory Approval | 08/07/2024 | 18/07/2024 | Completed
M0216 | P054 | General Availability | 12/08/2024 |  | Delayed
M0217 | P055 | Requirements & Scoping | 14/06/2024 |  | Delayed
M0218 | P055 | MVP Ready | 22/07/2024 | 13/08/2024 | Completed
M0219 | P055 | Regulatory Approval | 29/08/2024 |  | Delayed
M0220 | P055 | General Availability | 07/10/2024 |  | Delayed
M0221 | P056 | Requirements & Scoping | 06/02/2025 | 05/02/2025 | Completed
M0222 | P056 | MVP Ready | 08/03/2025 | 09/03/2025 | Completed
M0223 | P056 | Regulatory Approval | 07/04/2025 |  | On Track
M0224 | P056 | General Availability | 07/05/2025 |  | On Track
M0225 | P057 | Requirements & Scoping | 04/03/2025 | 03/03/2025 | Completed
M0226 | P057 | MVP Ready | 05/04/2025 | 02/04/2025 | Completed
M0227 | P057 | Regulatory Approval | 07/05/2025 |  | On Track
M0228 | P057 | General Availability | 08/06/2025 |  | On Track
M0229 | P058 | Requirements & Scoping | 17/02/2026 |  | On Track
M0230 | P058 | MVP Ready | 11/04/2026 |  | On Track
M0231 | P058 | Regulatory Approval | 02/06/2026 |  | On Track
M0232 | P058 | General Availability | 25/07/2026 |  | On Track
M0233 | P059 | Requirements & Scoping | 01/07/2025 | 01/07/2025 | Completed
M0234 | P059 | MVP Ready | 27/08/2025 | 28/08/2025 | Completed
M0235 | P059 | Regulatory Approval | 22/10/2025 |  | On Track
M0236 | P059 | General Availability | 18/12/2025 |  | On Track
M0237 | P060 | Requirements & Scoping | 22/09/2025 | 21/09/2025 | Completed
M0238 | P060 | MVP Ready | 10/12/2025 |  | On Track
M0239 | P060 | Regulatory Approval | 26/02/2026 |  | On Track
M0240 | P060 | General Availability | 16/05/2026 |  | On Track
M0241 | P061 | Requirements & Scoping | 07/11/2025 |  | On Track
M0242 | P061 | MVP Ready | 28/12/2025 |  | On Track
M0243 | P061 | Regulatory Approval | 16/02/2026 |  | On Track
M0244 | P061 | General Availability | 08/04/2026 |  | On Track
M0245 | P062 | Requirements & Scoping | 29/09/2025 | 06/10/2025 | Completed
M0246 | P062 | MVP Ready | 12/12/2025 |  | On Track
M0247 | P062 | Regulatory Approval | 24/02/2026 |  | On Track
M0248 | P062 | General Availability | 09/05/2026 |  | On Track
M0249 | P063 | Requirements & Scoping | 30/12/2025 |  | On Track
M0250 | P063 | MVP Ready | 26/02/2026 |  | On Track
M0251 | P063 | Regulatory Approval | 24/04/2026 |  | On Track
M0252 | P063 | General Availability | 21/06/2026 |  | On Track
M0253 | P064 | Requirements & Scoping | 04/06/2024 |  | Delayed
M0254 | P064 | MVP Ready | 05/07/2024 |  | Delayed
M0255 | P064 | Regulatory Approval | 05/08/2024 |  | Delayed
M0256 | P064 | General Availability | 06/09/2024 |  | Delayed
M0257 | P065 | Requirements & Scoping | 06/06/2025 | 01/06/2025 | Completed
M0258 | P065 | MVP Ready | 28/07/2025 | 27/07/2025 | Completed
M0259 | P065 | Regulatory Approval | 18/09/2025 |  | On Track
M0260 | P065 | General Availability | 09/11/2025 |  | On Track
M0261 | P066 | Requirements & Scoping | 18/03/2024 | 06/04/2024 | Completed
M0262 | P066 | MVP Ready | 25/04/2024 | 07/05/2024 | Completed
M0263 | P066 | Regulatory Approval | 02/06/2024 | 17/06/2024 | Completed
M0264 | P066 | General Availability | 11/07/2024 | 25/07/2024 | Completed
M0265 | P067 | Requirements & Scoping | 04/10/2025 | 08/10/2025 | Completed
M0266 | P067 | MVP Ready | 09/11/2025 |  | On Track
M0267 | P067 | Regulatory Approval | 15/12/2025 |  | On Track
M0268 | P067 | General Availability | 20/01/2026 |  | On Track
M0269 | P068 | Requirements & Scoping | 23/01/2026 |  | On Track
M0270 | P068 | MVP Ready | 09/03/2026 |  | On Track
M0271 | P068 | Regulatory Approval | 23/04/2026 |  | On Track
M0272 | P068 | General Availability | 07/06/2026 |  | On Track
M0273 | P069 | Requirements & Scoping | 01/07/2024 | 14/07/2024 | Completed
M0274 | P069 | MVP Ready | 08/09/2024 | 12/09/2024 | Completed
M0275 | P069 | Regulatory Approval | 16/11/2024 | 20/11/2024 | Completed
M0276 | P069 | General Availability | 24/01/2025 | 18/01/2025 | Completed
M0277 | P070 | Requirements & Scoping | 27/05/2024 |  | Delayed
M0278 | P070 | MVP Ready | 21/07/2024 | 03/08/2024 | Completed
M0279 | P070 | Regulatory Approval | 14/09/2024 | 27/09/2024 | Completed
M0280 | P070 | General Availability | 09/11/2024 |  | Delayed
M0281 | P071 | Requirements & Scoping | 18/04/2026 |  | On Track
M0282 | P071 | MVP Ready | 30/05/2026 |  | On Track
M0283 | P071 | Regulatory Approval | 11/07/2026 |  | On Track
M0284 | P071 | General Availability | 23/08/2026 |  | On Track
M0285 | P072 | Requirements & Scoping | 08/10/2025 | 09/10/2025 | Completed
M0286 | P072 | MVP Ready | 01/12/2025 |  | On Track
M0287 | P072 | Regulatory Approval | 23/01/2026 |  | On Track
M0288 | P072 | General Availability | 18/03/2026 |  | On Track

## Employees
EmployeeID | FullName | DepartmentID | Role | ExperienceLevel | Country | City | Employee_Country_Latitude | Employee_Country_Longitude | HourlyRate (EUR/hour)
E001 | Johan Moretti | D03 | Data Analyst | Junior | Sweden | Stockholm | 59.337159 | 18.060046 | 27
E002 | Noemi Popescu | D03 | Data Analyst | Mid | Netherlands | Eindhoven | 51.443653 | 5.478479 | 56
E003 | Sara Dubois | D01 | UX Designer | Mid | Finland | Helsinki | 60.189131 | 24.945793 | 56
E004 | Kasper Kaczmarek | D02 | Project Manager | Mid | Greece | Patras | 38.242285 | 21.728327 | 40
E005 | Agnieszka Nielsen | D02 | QA Engineer | Mid | Netherlands | Eindhoven | 51.439143 | 5.452087 | 45
E006 | Kai Moretti | D03 | BI Developer | Mid | Italy | Rome | 41.91232 | 12.4837 | 59
E007 | Helena Nielsen | D02 | DevOps Engineer | Senior | Czechia | Ostrava | 49.822162 | 18.263773 | 91
E008 | Giulia Fischer | D02 | Project Manager | Mid | Poland | Krakow | 50.078677 | 19.953978 | 41
E009 | Anna Lindberg | D02 | Project Manager | Senior | Finland | Turku | 60.460698 | 22.259518 | 94
E010 | Zuzanna Martin | D02 | Project Manager | Senior | Finland | Tampere | 61.486931 | 23.752749 | 98
E011 | Elisa Kovač | D01 | Project Manager | Senior | Hungary | Pécs | 46.056384 | 18.229648 | 95
E012 | Clara Weber | D02 | Project Manager | Junior | Finland | Tampere | 61.497547 | 23.758033 | 26
E013 | Mateusz Kovačić | D01 | Business Analyst | Senior | Ireland | Cork | 51.895554 | -8.459864 | 82
E014 | Zuzanna Gruber | D03 | Data Scientist | Senior | Austria | Graz | 47.070773 | 15.444458 | 91
E015 | Emil Mendes | D07 | Support Specialist | Mid | Denmark | Odense | 55.396491 | 10.398993 | 55
E016 | Sven Nováková | D07 | Customer Support Lead | Junior | Czechia | Plzeň | 49.728418 | 13.372921 | 40
E017 | Jean Silva | D04 | Legal Analyst | Mid | Greece | Larissa | 39.639779 | 22.423616 | 58
E018 | Helena Horváth | D01 | UX Designer | Senior | Sweden | Linköping | 58.423854 | 15.625522 | 71
E019 | Emil Santos | D06 | Controller | Mid | Portugal | Faro | 37.013111 | -7.938235 | 50
E020 | Ivana Kaczmarek | D06 | Finance Analyst | Mid | Finland | Espoo | 60.212752 | 24.670918 | 56
E021 | Ilias Schneider | D04 | Compliance Specialist | Senior | Portugal | Porto | 41.164673 | -8.625663 | 85
E022 | João Santos | D07 | Support Specialist | Mid | Germany | Hamburg | 53.558088 | 10.007394 | 54
E023 | Anna O'Connor | D04 | Compliance Specialist | Junior | Hungary | Debrecen | 47.542147 | 21.617047 | 26
E024 | Bjorn Fischer | D05 | Content Manager | Senior | Portugal | Coimbra | 40.206198 | -8.426471 | 61
E025 | Kasper Müller | D06 | Controller | Junior | Hungary | Budapest | 47.50299 | 19.049137 | 26
E026 | Zuzanna Greco | D01 | Business Analyst | Mid | Poland | Poznan | 52.410177 | 16.927471 | 58
E027 | Irene Andersen | D07 | Customer Support Lead | Mid | Finland | Oulu | 64.998223 | 25.472921 | 45
E028 | Sara Dumitrescu | D05 | Digital Strategist | Junior | Czechia | Plzeň | 49.746079 | 13.375775 | 35
E029 | Sofia Marin | D03 | Project Manager | Mid | Poland | Krakow | 50.081705 | 19.958667 | 48
E030 | Erik Müller | D07 | Customer Support Lead | Junior | Poland | Warsaw | 52.211444 | 21.004391 | 36
E031 | João Müller | D02 | Software Engineer | Mid | Ireland | Waterford | 52.267498 | -7.090286 | 59
E032 | Marie Müller | D01 | UX Designer | Junior | Czechia | Ostrava | 49.831402 | 18.266227 | 28
E033 | Sara Nováková | D07 | Support Specialist | Junior | Ireland | Cork | 51.884545 | -8.479645 | 28
E034 | Carlos Müller | D03 | Data Scientist | Senior | Romania | Cluj-Napoca | 46.764938 | 23.624125 | 98
E035 | Ilias Ricci | D02 | DevOps Engineer | Senior | Finland | Turku | 60.436036 | 22.251836 | 87
E036 | Marie Pereira | D02 | Software Engineer | Senior | France | Marseille | 43.302963 | 5.38366 | 84
E037 | Ivana Ricci | D01 | Business Analyst | Senior | Netherlands | Amsterdam | 52.381778 | 4.899494 | 75
E038 | Emil Costa | D02 | Project Manager | Mid | Germany | Hamburg | 53.545271 | 9.980543 | 42
E039 | Emil Papadopoulos | D03 | Data Scientist | Mid | Finland | Helsinki | 60.163447 | 24.940495 | 45
E040 | Erik Rossi | D01 | UX Designer | Mid | Ireland | Dublin | 53.350661 | -6.280192 | 60
E041 | Emma Keller | D05 | Marketing Specialist | Senior | Belgium | Liège | 50.648814 | 5.568005 | 62
E042 | Bjorn Costa | D01 | Product Owner | Senior | Germany | Munich | 48.1359 | 11.598076 | 96
E043 | Clara Moretti | D05 | Marketing Specialist | Mid | Italy | Milan | 45.454502 | 9.192574 | 54
E044 | Elisa Virtanen | D02 | QA Engineer | Junior | Finland | Helsinki | 60.165675 | 24.947643 | 35
E045 | Miguel Pietrzak | D01 | Project Manager | Mid | Netherlands | Amsterdam | 52.371628 | 4.918735 | 48
E046 | Kasper Costa | D02 | Project Manager | Senior | Sweden | Gothenburg | 57.692075 | 11.971734 | 92
E047 | Helena Petrescu | D05 | Digital Strategist | Mid | Spain | Madrid | 40.414825 | -3.701889 | 53
E048 | Kasper García | D02 | Project Manager | Mid | Sweden | Stockholm | 59.321174 | 18.085703 | 50
E049 | Giulia Dumitrescu | D01 | Project Manager | Senior | Portugal | Porto | 41.156196 | -8.618959 | 99
E050 | Jean Nagy | D01 | UX Designer | Senior | Denmark | Aalborg | 57.030743 | 9.930048 | 74
E051 | Hugo García | D07 | Implementation Specialist | Mid | Netherlands | Utrecht | 52.077338 | 5.13264 | 50
E052 | Oliver Santos | D06 | Procurement Specialist | Mid | Ireland | Dublin | 53.342059 | -6.25369 | 53
E053 | Stefan Virtanen | D05 | Content Manager | Mid | Portugal | Lisbon | 38.728895 | -9.123786 | 47
E054 | Daria Kovač | D02 | Software Engineer | Mid | Italy | Bologna | 44.492513 | 11.340129 | 48
E055 | Sofia Ivanov | D07 | Implementation Specialist | Junior | Spain | Barcelona | 41.387726 | 2.156796 | 25
E056 | Marta Fischer | D02 | QA Engineer | Senior | Portugal | Faro | 37.031994 | -7.936917 | 61
E057 | Lukas Mendes | D07 | Customer Support Lead | Mid | Denmark | Copenhagen | 55.686129 | 12.571263 | 48
E058 | Marie Pietrzak | D05 | Content Manager | Mid | Poland | Wroclaw | 51.091066 | 17.052876 | 48
E059 | Adrian Papadopoulos | D02 | Software Engineer | Mid | Italy | Turin | 45.086695 | 7.672045 | 53
E060 | Nina Zieliński | D01 | UX Designer | Mid | Denmark | Odense | 55.389337 | 10.398375 | 56
E061 | Tomás Marin | D01 | Product Owner | Mid | Hungary | Pécs | 46.075189 | 18.21719 | 41
E062 | Heidi Nowak | D06 | Procurement Specialist | Mid | Ireland | Galway | 53.283166 | -9.05808 | 59
E063 | Jean Zieliński | D05 | Content Manager | Senior | Portugal | Coimbra | 40.183597 | -8.408236 | 61
E064 | Anna Dupont | D07 | Customer Support Lead | Junior | Italy | Bologna | 44.498187 | 11.330844 | 38
E065 | Mikkel Nowicka | D01 | Business Analyst | Senior | Austria | Graz | 47.065859 | 15.446235 | 72
E066 | Stefan Santos | D05 | Marketing Specialist | Mid | Czechia | Brno | 49.200536 | 16.588088 | 53
E067 | Kai Nowicka | D02 | Software Engineer | Mid | Spain | Barcelona | 41.384017 | 2.15827 | 45
E068 | Emma Dupont | D03 | BI Developer | Junior | Finland | Tampere | 61.480471 | 23.767135 | 33
E069 | Elisa Moretti | D01 | Project Manager | Senior | Finland | Tampere | 61.508576 | 23.763951 | 91
E070 | Elena Fischer | D03 | Data Engineer | Senior | Portugal | Faro | 37.027393000000004 | -7.923953 | 84
E071 | Katalin Bianchi | D03 | Data Scientist | Senior | Netherlands | The Hague | 52.082192 | 4.301449 | 95
E072 | Sofia Rossi | D02 | Project Manager | Mid | Greece | Athens | 37.995327 | 23.723963 | 44
E073 | Noemi Svensson | D02 | Project Manager | Senior | Netherlands | Rotterdam | 51.911665 | 4.470553 | 65
E074 | Heidi Jensen | D04 | Risk Analyst | Junior | Spain | Seville | 37.376576 | -5.987808 | 29
E075 | Patrick Schmidt | D03 | Data Engineer | Mid | Czechia | Liberec | 50.756564 | 15.073173 | 44
E076 | Johan Schmidt | D07 | Customer Support Lead | Senior | Poland | Warsaw | 52.213352 | 21.010746 | 96
E077 | Stefan Greco | D02 | Project Manager | Senior | Germany | Munich | 48.127647 | 11.563894 | 92
E078 | Kai Weber | D04 | Compliance Specialist | Senior | Hungary | Budapest | 47.481721 | 19.02973 | 87
E079 | Nikos Dumitrescu | D07 | Customer Support Lead | Senior | Greece | Larissa | 39.654799 | 22.400829 | 87
E080 | Oliver Nowicka | D02 | Project Manager | Mid | Finland | Oulu | 65.031323 | 25.46668 | 56
E081 | Clara Santos | D04 | Compliance Specialist | Junior | Poland | Krakow | 50.044922 | 19.944396 | 30
E082 | Filip Fischer | D04 | Risk Analyst | Junior | Portugal | Braga | 41.540407 | -8.442618 | 36
E083 | Filip Nagy | D03 | Data Scientist | Mid | Belgium | Bruges | 51.22782 | 3.218373 | 44
E084 | Tomás Kovač | D03 | Data Analyst | Senior | Germany | Cologne | 50.949454 | 6.94863 | 70
E085 | Marek Moretti | D03 | Data Engineer | Mid | Italy | Naples | 40.860424 | 14.264521 | 60
E086 | Lea Moretti | D06 | Finance Analyst | Mid | Greece | Athens | 38.0025 | 23.73353 | 59
E087 | Marie Rossi | D02 | Project Manager | Mid | Portugal | Faro | 37.00041 | -7.939724 | 40
E088 | Emil Nowicka | D05 | Content Manager | Mid | Ireland | Cork | 51.881198 | -8.455879 | 44
E089 | Daria Bianchi | D01 | Product Owner | Mid | Greece | Patras | 38.241572 | 21.72316 | 54
E090 | Lukas Kaczmarek | D05 | Content Manager | Junior | Italy | Bologna | 44.484199 | 11.334624 | 38
E091 | Emil Martin | D01 | Business Analyst | Senior | Hungary | Budapest | 47.489149 | 19.034691 | 71
E092 | Emil Silva | D05 | Digital Strategist | Senior | Sweden | Linköping | 58.405429 | 15.622755 | 67
E093 | Sara Bianchi | D03 | Data Scientist | Senior | Czechia | Ostrava | 49.824797 | 18.254226 | 98
E094 | Sofia Nagy | D02 | DevOps Engineer | Junior | France | Lille | 50.610248 | 3.072804 | 35
E095 | Kai Novak | D04 | Compliance Specialist | Mid | France | Lyon | 45.749078 | 4.846786 | 41
E096 | Marie Kowalska | D01 | Business Analyst | Mid | Finland | Espoo | 60.21394 | 24.674742 | 47
E097 | Marek Ricci | D05 | Marketing Specialist | Mid | Belgium | Liège | 50.641006 | 5.59804 | 51
E098 | Marek Dupont | D03 | Data Analyst | Mid | Denmark | Odense | 55.418715 | 10.396638 | 60
E099 | Giulia García | D07 | Implementation Specialist | Mid | Sweden | Stockholm | 59.315251 | 18.086201 | 54
E100 | Emil Jensen | D02 | Project Manager | Mid | Ireland | Dublin | 53.363642 | -6.275343 | 40
E101 | Giulia Huber | D03 | BI Developer | Mid | Ireland | Limerick | 52.644456 | -8.617853 | 57
E102 | Sara Weber | D02 | Software Engineer | Mid | Austria | Linz | 48.290293 | 14.27482 | 47
E103 | Nina Rossi | D02 | QA Engineer | Mid | Greece | Larissa | 39.633543 | 22.420698 | 47
E104 | João Moretti | D04 | Risk Analyst | Junior | Belgium | Antwerp | 51.208419 | 4.405386 | 36
E105 | Elena Mendes | D04 | Compliance Specialist | Senior | Greece | Heraklion | 35.33063 | 25.140945 | 83
E106 | Anja Rossi | D03 | Data Analyst | Mid | Netherlands | The Hague | 52.087794 | 4.3042 | 60
E107 | Helena Nováková | D07 | Support Specialist | Mid | Spain | Valencia | 39.472141 | -0.376278 | 43
E108 | Marie Kovač | D02 | Software Engineer | Mid | Hungary | Budapest | 47.497136 | 19.057298 | 45
E109 | Johan Greco | D03 | BI Developer | Mid | Greece | Athens | 37.965884 | 23.723771 | 60
E110 | Carlos Pereira | D05 | Marketing Specialist | Mid | Ireland | Limerick | 52.678086 | -8.645636 | 54
E111 | Marta Schmidt | D04 | Compliance Specialist | Mid | Austria | Innsbruck | 47.276436 | 11.420269 | 53
E112 | Luca Baumann | D07 | Customer Support Lead | Junior | Spain | Madrid | 40.429278 | -3.710378 | 36
E113 | Kai Pereira | D02 | Software Engineer | Senior | Czechia | Plzeň | 49.733995 | 13.383792 | 82
E114 | Tomas Gruber | D07 | Support Specialist | Senior | France | Toulouse | 43.594389 | 1.461707 | 77
E115 | Agnieszka Dumitrescu | D01 | UX Designer | Senior | Finland | Oulu | 65.006052 | 25.470486 | 68
E116 | Sofia O'Connor | D05 | Content Manager | Mid | Austria | Vienna | 48.196445 | 16.367254 | 45
E117 | Erik Lindberg | D02 | Software Engineer | Junior | Finland | Turku | 60.467091 | 22.279492 | 29
E118 | Helena Schmidt | D02 | Project Manager | Senior | Ireland | Galway | 53.289074 | -9.059898 | 93
E119 | Ivana Mendes | D01 | Business Analyst | Mid | France | Lille | 50.613896 | 3.049342 | 58
E120 | Tomas Petrescu | D02 | Software Engineer | Mid | Greece | Larissa | 39.622687 | 22.423217 | 44

## Departments
Department_ID | Department_Name | Head_Of_Department
D01 | Product Management | Giulia Dumitrescu
D02 | Engineering | Marta Fischer
D03 | Data & Analytics | Sara Bianchi
D04 | Compliance & Risk | Kai Weber
D05 | Marketing | Jean Zieliński
D06 | Finance | Heidi Nowak
D07 | Customer Support | Nikos Dumitrescu

## Tasks
TaskID | ProjectID | AssignedTo (EmployeeID) | TaskName | PlannedHours | ActualHours | TaskStatus | Priority
T0001 | P001 | E024 | API Development - Phase 2 | 122 | 56 | In Progress | Medium
T0002 | P001 | E033 | KPI Definition - Optimization | 71 | 43 | In Progress | High
T0003 | P001 | E112 | User Acceptance Testing - Data Prep | 184 | 211 | Completed | High
T0004 | P001 | E114 | Requirement Gathering - Stabilization | 198 | 144 | In Progress | Low
T0005 | P001 | E033 | Security Audit - Deployment | 24 | 9 | In Progress | Medium
T0006 | P002 | E082 | User Acceptance Testing - Enhancement | 200 | 223 | Completed | High
T0007 | P002 | E095 | KPI Definition - Initial Setup | 38 | 30 | Completed | Medium
T0008 | P002 | E078 | Data Migration - Module C | 68 | 64 | Completed | High
T0009 | P002 | E101 | Mobile App Integration - Validation | 126 | 97 | Completed | Medium
T0010 | P003 | E078 | Mobile App Integration - Module A | 47 | 43 | Completed | Medium
T0011 | P003 | E021 | Security Audit - Configuration | 142 | 182 | Completed | Medium
T0012 | P003 | E105 | Requirement Gathering - Initial Setup | 122 | 127 | Completed | Medium
T0013 | P003 | E105 | CI/CD Setup - Module B | 137 | 157 | Completed | Medium
T0014 | P004 | E055 | KPI Definition - Initial Setup | 30 | 34 | Completed | Medium
T0015 | P004 | E067 | Mobile App Integration - Integration | 184 | 225 | Completed | Medium
T0016 | P004 | E107 | API Development - Stabilization | 177 | 202 | Completed | High
T0017 | P004 | E006 | Compliance Documentation - Validation | 92 | 84 | Completed | High
T0018 | P005 | E013 | Unit Testing - Data Prep | 133 | 102 | In Progress | Medium
T0019 | P005 | E040 | Mobile App Integration - Module A | 162 | 71 | In Progress | High
T0020 | P005 | E013 | User Acceptance Testing - Data Prep | 101 | 0 | Not Started | High
T0021 | P005 | E013 | API Development - Deployment | 132 | 76 | In Progress | Low
T0022 | P006 | E090 | Compliance Documentation - Validation | 38 | 8 | In Progress | Medium
T0023 | P006 | E025 | Marketing Launch Prep - Upgrade | 39 | 23 | In Progress | Low
T0024 | P006 | E024 | User Acceptance Testing - Refinement | 195 | 204 | Completed | Medium
T0025 | P006 | E025 | CI/CD Setup - Data Prep | 42 | 29 | In Progress | High
T0026 | P007 | E032 | CI/CD Setup - Phase 2 | 187 | 193 | Completed | High
T0027 | P007 | E037 | Mobile App Integration - Configuration | 71 | 70 | Completed | Medium
T0028 | P007 | E037 | Requirement Gathering - Validation | 40 | 40 | Completed | Medium
T0029 | P007 | E032 | Design Prototype - Review | 192 | 147 | Completed | Medium
T0030 | P008 | E050 | CI/CD Setup - Optimization | 150 | 181 | Completed | Medium
T0031 | P008 | E111 | KPI Definition - Refinement | 50 | 41 | Completed | High
T0032 | P008 | E057 | Compliance Documentation - Upgrade | 146 | 144 | Completed | Medium
T0033 | P008 | E081 | Mobile App Integration - Integration | 31 | 7 | In Progress | Medium
T0034 | P009 | E083 | KPI Definition - Phase 2 | 143 | 100 | Completed | Medium
T0035 | P009 | E083 | API Development - Initial Setup | 55 | 44 | Completed | High
T0036 | P009 | E083 | Mobile App Integration - Phase 1 | 109 | 49 | In Progress | Low
T0037 | P009 | E083 | Requirement Gathering - Optimization | 40 | 18 | In Progress | Medium
T0038 | P010 | E066 | Data Migration - Deployment | 136 | 148 | Completed | Medium
T0039 | P010 | E016 | Security Audit - Refinement | 106 | 133 | Completed | Medium
T0040 | P010 | E007 | KPI Definition - Review | 96 | 70 | In Progress | Medium
T0041 | P010 | E066 | Mobile App Integration - Deployment | 70 | 50 | Completed | Medium
T0042 | P011 | E047 | KPI Definition - Module C | 197 | 129 | In Progress | Low
T0043 | P011 | E047 | User Acceptance Testing - Enhancement | 100 | 92 | Completed | High
T0044 | P011 | E047 | CI/CD Setup - Review | 199 | 232 | Completed | High
T0045 | P011 | E047 | Marketing Launch Prep - Initial Setup | 117 | 90 | Completed | Medium
T0046 | P012 | E062 | Design Prototype - Compliance | 113 | 79 | In Progress | Medium
T0047 | P012 | E052 | Marketing Launch Prep - Validation | 105 | 136 | Completed | Medium
T0048 | P012 | E086 | Unit Testing - Validation | 32 | 15 | In Progress | Medium
T0049 | P012 | E071 | User Acceptance Testing - Integration | 51 | 17 | In Progress | Low
T0050 | P012 | E051 | API Development - Deployment | 196 | 73 | In Progress | Medium
T0051 | P013 | E024 | Compliance Documentation - Phase 1 | 121 | 56 | In Progress | Low
T0052 | P013 | E058 | User Acceptance Testing - Testing | 34 | 23 | In Progress | Low
T0053 | P013 | E002 | API Development - Data Prep | 95 | 78 | Completed | Medium
T0054 | P013 | E097 | Security Audit - Testing | 69 | 76 | Completed | Medium
T0055 | P014 | E055 | Mobile App Integration - Enhancement | 87 | 103 | Completed | Medium
T0056 | P014 | E022 | Security Audit - Enhancement | 160 | 41 | In Progress | Medium
T0057 | P014 | E030 | Marketing Launch Prep - Compliance | 196 | 0 | Not Started | Medium
T0058 | P014 | E087 | Requirement Gathering - Optimization | 75 | 0 | Not Started | Low
T0059 | P015 | E015 | API Development - Compliance | 190 | 132 | In Progress | Low
T0060 | P015 | E015 | User Acceptance Testing - Data Prep | 86 | 0 | Not Started | Medium
T0061 | P015 | E050 | Security Audit - Phase 2 | 192 | 109 | In Progress | Medium
T0062 | P015 | E057 | Data Migration - Module C | 46 | 52 | Completed | Low
T0063 | P016 | E076 | CI/CD Setup - Module A | 107 | 152 | Completed | High
T0064 | P016 | E030 | Design Prototype - Deployment | 161 | 205 | Completed | Medium
T0065 | P016 | E076 | Requirement Gathering - Configuration | 139 | 83 | In Progress | High
T0066 | P016 | E076 | Data Migration - Phase 2 | 147 | 134 | Completed | Medium
T0067 | P017 | E043 | Requirement Gathering - Compliance | 150 | 117 | In Progress | High
T0068 | P017 | E024 | Compliance Documentation - Enhancement | 100 | 118 | Completed | Medium
T0069 | P017 | E092 | CI/CD Setup - Upgrade | 130 | 74 | In Progress | Low
T0070 | P017 | E090 | User Acceptance Testing - Review | 32 | 38 | Completed | High
T0071 | P018 | E076 | Design Prototype - Data Prep | 99 | 0 | Not Started | Medium
T0072 | P018 | E030 | API Development - Module A | 145 | 49 | In Progress | High
T0073 | P018 | E076 | CI/CD Setup - Review | 187 | 80 | In Progress | Medium
T0074 | P018 | E030 | KPI Definition - Phase 1 | 83 | 66 | In Progress | Low
T0075 | P019 | E113 | Security Audit - Module B | 182 | 153 | Completed | Low
T0076 | P019 | E056 | KPI Definition - Refinement | 114 | 93 | Completed | Low
T0077 | P019 | E104 | Mobile App Integration - Review | 151 | 121 | Completed | Medium
T0078 | P019 | E104 | Unit Testing - Finalization | 131 | 121 | Completed | Medium
T0079 | P020 | E030 | Mobile App Integration - Review | 95 | 0 | Not Started | Medium
T0080 | P020 | E015 | CI/CD Setup - Finalization | 104 | 0 | Not Started | High
T0081 | P020 | E107 | KPI Definition - Module B | 47 | 0 | Not Started | Low
T0082 | P020 | E016 | Data Migration - Review | 176 | 0 | Not Started | High
T0083 | P021 | E036 | Requirement Gathering - Integration | 166 | 108 | In Progress | Low
T0084 | P021 | E036 | CI/CD Setup - Module A | 94 | 76 | Completed | Medium
T0085 | P021 | E094 | Design Prototype - Validation | 119 | 129 | Completed | Medium
T0086 | P021 | E094 | Marketing Launch Prep - Finalization | 35 | 13 | In Progress | High
T0087 | P022 | E077 | Mobile App Integration - Phase 1 | 184 | 60 | In Progress | Medium
T0088 | P022 | E012 | Data Migration - Testing | 25 | 19 | In Progress | High
T0089 | P022 | E036 | Security Audit - Module C | 90 | 40 | In Progress | Medium
T0090 | P022 | E080 | Marketing Launch Prep - Configuration | 98 | 102 | Completed | Medium
T0091 | P023 | E023 | API Development - Integration | 115 | 55 | In Progress | Medium
T0092 | P023 | E058 | CI/CD Setup - Phase 1 | 117 | 75 | In Progress | Medium
T0093 | P023 | E090 | Data Migration - Deployment | 86 | 86 | Completed | Medium
T0094 | P023 | E028 | Compliance Documentation - Configuration | 70 | 78 | Completed | Medium
T0095 | P023 | E023 | Mobile App Integration - Module A | 172 | 0 | Not Started | Medium
T0096 | P024 | E059 | Design Prototype - Configuration | 137 | 146 | Completed | High
T0097 | P024 | E054 | User Acceptance Testing - Data Prep | 195 | 0 | Not Started | High
T0098 | P024 | E054 | CI/CD Setup - Configuration | 87 | 105 | Completed | Medium
T0099 | P024 | E059 | Data Migration - Finalization | 76 | 87 | Completed | Medium
T0100 | P025 | E087 | Design Prototype - Enhancement | 27 | 20 | In Progress | Medium
T0101 | P025 | E087 | KPI Definition - Enhancement | 198 | 150 | In Progress | Low
T0102 | P025 | E087 | Security Audit - Upgrade | 98 | 67 | In Progress | Medium
T0103 | P025 | E087 | CI/CD Setup - Refinement | 181 | 0 | Not Started | Medium
T0104 | P026 | E102 | API Development - Deployment | 188 | 143 | In Progress | Medium
T0105 | P026 | E102 | Data Migration - Validation | 48 | 38 | In Progress | Medium
T0106 | P026 | E102 | Compliance Documentation - Finalization | 97 | 84 | In Progress | Medium
T0107 | P026 | E102 | Marketing Launch Prep - Compliance | 192 | 149 | In Progress | High
T0108 | P027 | E072 | Mobile App Integration - Enhancement | 190 | 152 | Completed | Medium
T0109 | P027 | E024 | Marketing Launch Prep - Module B | 198 | 201 | Completed | High
T0110 | P027 | E086 | API Development - Module A | 67 | 31 | In Progress | Medium
T0111 | P027 | E116 | CI/CD Setup - Initial Setup | 115 | 53 | In Progress | High
T0112 | P028 | E025 | Mobile App Integration - Review | 113 | 87 | In Progress | Medium
T0113 | P028 | E097 | CI/CD Setup - Testing | 104 | 51 | In Progress | Medium
T0114 | P028 | E062 | API Development - Phase 1 | 51 | 46 | Completed | Medium
T0115 | P028 | E025 | Design Prototype - Optimization | 36 | 17 | In Progress | High
T0116 | P029 | E056 | Unit Testing - Compliance | 70 | 15 | In Progress | Medium
T0117 | P029 | E087 | Compliance Documentation - Compliance | 56 | 41 | In Progress | High
T0118 | P029 | E087 | CI/CD Setup - Upgrade | 91 | 89 | Completed | Medium
T0119 | P029 | E087 | Design Prototype - Finalization | 78 | 25 | In Progress | High
T0120 | P030 | E062 | Mobile App Integration - Compliance | 29 | 30 | Completed | Low
T0121 | P030 | E081 | CI/CD Setup - Integration | 129 | 138 | Completed | Low
T0122 | P030 | E019 | Requirement Gathering - Phase 2 | 29 | 0 | Not Started | Medium
T0123 | P030 | E058 | Unit Testing - Phase 1 | 117 | 152 | Completed | Medium
T0124 | P031 | E072 | Security Audit - Refinement | 89 | 9 | In Progress | High
T0125 | P031 | E120 | CI/CD Setup - Module B | 73 | 0 | Not Started | Low
T0126 | P031 | E120 | Design Prototype - Configuration | 137 | 0 | Not Started | Low
T0127 | P031 | E103 | Mobile App Integration - Finalization | 175 | 0 | Not Started | Medium
T0128 | P032 | E062 | Marketing Launch Prep - Testing | 182 | 0 | Not Started | High
T0129 | P032 | E019 | Unit Testing - Phase 1 | 36 | 8 | In Progress | Medium
T0130 | P032 | E041 | Requirement Gathering - Phase 1 | 41 | 32 | Completed | High
T0131 | P032 | E083 | Design Prototype - Enhancement | 89 | 66 | In Progress | High
T0132 | P033 | E027 | CI/CD Setup - Phase 2 | 159 | 52 | In Progress | High
T0133 | P033 | E027 | Unit Testing - Integration | 187 | 97 | In Progress | Low
T0134 | P033 | E027 | Design Prototype - Configuration | 82 | 58 | Completed | Medium
T0135 | P033 | E027 | Marketing Launch Prep - Deployment | 200 | 207 | Completed | High
T0136 | P033 | E027 | User Acceptance Testing - Validation | 153 | 91 | In Progress | Low
T0137 | P034 | E099 | Mobile App Integration - Configuration | 143 | 132 | Completed | Medium
T0138 | P034 | E099 | Security Audit - Data Prep | 142 | 100 | In Progress | High
T0139 | P034 | E099 | KPI Definition - Module C | 108 | 129 | Completed | Low
T0140 | P034 | E099 | Data Migration - Optimization | 77 | 0 | Not Started | Medium
T0141 | P035 | E086 | Compliance Documentation - Data Prep | 169 | 70 | In Progress | High
T0142 | P035 | E086 | Mobile App Integration - Enhancement | 103 | 92 | Completed | High
T0143 | P035 | E074 | Marketing Launch Prep - Optimization | 132 | 133 | Completed | Medium
T0144 | P035 | E107 | User Acceptance Testing - Optimization | 141 | 160 | Completed | Medium
T0145 | P036 | E098 | Data Migration - Stabilization | 183 | 232 | Completed | High
T0146 | P036 | E098 | Requirement Gathering - Data Prep | 163 | 101 | In Progress | High
T0147 | P036 | E098 | Design Prototype - Phase 1 | 59 | 49 | In Progress | Medium
T0148 | P036 | E098 | KPI Definition - Stabilization | 104 | 118 | Completed | Medium
T0149 | P036 | E098 | Compliance Documentation - Module C | 56 | 46 | In Progress | High
T0150 | P037 | E058 | Design Prototype - Compliance | 188 | 0 | Not Started | High
T0151 | P037 | E058 | Data Migration - Validation | 190 | 0 | Not Started | Medium
T0152 | P037 | E058 | User Acceptance Testing - Review | 111 | 0 | Not Started | Medium
T0153 | P037 | E058 | Mobile App Integration - Compliance | 103 | 0 | Not Started | Low
T0154 | P037 | E058 | Requirement Gathering - Review | 27 | 0 | Not Started | Medium
T0155 | P038 | E047 | Marketing Launch Prep - Deployment | 144 | 141 | Completed | Medium
T0156 | P038 | E067 | KPI Definition - Testing | 36 | 0 | Not Started | Medium
T0157 | P038 | E047 | Mobile App Integration - Module C | 69 | 48 | In Progress | Medium
T0158 | P038 | E020 | Security Audit - Stabilization | 81 | 29 | In Progress | Low
T0159 | P039 | E074 | CI/CD Setup - Data Prep | 185 | 46 | In Progress | Low
T0160 | P039 | E074 | API Development - Compliance | 54 | 37 | In Progress | Low
T0161 | P039 | E074 | KPI Definition - Finalization | 117 | 52 | In Progress | Medium
T0162 | P039 | E074 | Compliance Documentation - Module A | 152 | 199 | Completed | High
T0163 | P040 | E047 | Compliance Documentation - Testing | 79 | 31 | In Progress | Medium
T0164 | P040 | E047 | CI/CD Setup - Data Prep | 184 | 0 | Not Started | Medium
T0165 | P040 | E047 | Unit Testing - Optimization | 155 | 102 | In Progress | High
T0166 | P040 | E047 | KPI Definition - Validation | 137 | 100 | In Progress | Medium
T0167 | P041 | E065 | Design Prototype - Stabilization | 43 | 15 | In Progress | Low
T0168 | P041 | E089 | Data Migration - Module A | 96 | 118 | Completed | High
T0169 | P041 | E026 | Requirement Gathering - Initial Setup | 158 | 124 | Completed | Low
T0170 | P041 | E003 | CI/CD Setup - Module C | 168 | 131 | In Progress | Medium
T0171 | P042 | E071 | Unit Testing - Validation | 37 | 35 | Completed | Medium
T0172 | P042 | E002 | Marketing Launch Prep - Review | 78 | 91 | Completed | Medium
T0173 | P042 | E002 | Design Prototype - Stabilization | 66 | 70 | Completed | Low
T0174 | P042 | E106 | CI/CD Setup - Compliance | 44 | 48 | Completed | Low
T0175 | P043 | E034 | User Acceptance Testing - Deployment | 106 | 0 | Not Started | Medium
T0176 | P043 | E034 | KPI Definition - Testing | 42 | 0 | Not Started | Medium
T0177 | P043 | E034 | Data Migration - Data Prep | 49 | 0 | Not Started | Low
T0178 | P043 | E019 | Security Audit - Phase 1 | 145 | 0 | Not Started | High
T0179 | P044 | E105 | Design Prototype - Phase 1 | 119 | 51 | In Progress | Medium
T0180 | P044 | E105 | API Development - Deployment | 91 | 114 | Completed | Medium
T0181 | P044 | E017 | Data Migration - Enhancement | 44 | 17 | In Progress | High
T0182 | P044 | E105 | KPI Definition - Validation | 43 | 28 | In Progress | Medium
T0183 | P045 | E018 | Compliance Documentation - Enhancement | 94 | 116 | Completed | Medium
T0184 | P045 | E018 | Marketing Launch Prep - Refinement | 46 | 61 | Completed | Medium
T0185 | P045 | E018 | CI/CD Setup - Finalization | 137 | 99 | In Progress | Low
T0186 | P045 | E018 | Unit Testing - Testing | 62 | 46 | In Progress | Medium
T0187 | P045 | E018 | Security Audit - Testing | 132 | 82 | In Progress | Medium
T0188 | P046 | E086 | Data Migration - Validation | 47 | 0 | Not Started | High
T0189 | P046 | E057 | KPI Definition - Data Prep | 198 | 65 | In Progress | Medium
T0190 | P046 | E025 | Compliance Documentation - Initial Setup | 51 | 32 | In Progress | Medium
T0191 | P046 | E050 | Unit Testing - Review | 80 | 77 | Completed | Low
T0192 | P047 | E018 | API Development - Compliance | 196 | 241 | Completed | Low
T0193 | P047 | E026 | Mobile App Integration - Enhancement | 36 | 42 | Completed | Medium
T0194 | P047 | E018 | KPI Definition - Enhancement | 173 | 215 | Completed | High
T0195 | P047 | E013 | Data Migration - Phase 1 | 111 | 127 | Completed | Medium
T0196 | P048 | E014 | Security Audit - Compliance | 158 | 164 | Completed | High
T0197 | P048 | E014 | Design Prototype - Module A | 168 | 70 | In Progress | High
T0198 | P048 | E014 | KPI Definition - Module A | 134 | 174 | Completed | Medium
T0199 | P048 | E014 | Data Migration - Module C | 130 | 93 | In Progress | Medium
T0200 | P048 | E014 | Mobile App Integration - Enhancement | 176 | 40 | In Progress | High
T0201 | P049 | E120 | Data Migration - Data Prep | 85 | 51 | In Progress | Medium
T0202 | P049 | E056 | User Acceptance Testing - Stabilization | 43 | 56 | Completed | Low
T0203 | P049 | E012 | Mobile App Integration - Deployment | 110 | 64 | In Progress | High
T0204 | P049 | E054 | KPI Definition - Configuration | 39 | 35 | Completed | High
T0205 | P050 | E062 | Unit Testing - Optimization | 78 | 58 | Completed | Low
T0206 | P050 | E062 | Security Audit - Module B | 141 | 123 | Completed | High
T0207 | P050 | E062 | Marketing Launch Prep - Module A | 66 | 59 | Completed | Medium
T0208 | P050 | E062 | Compliance Documentation - Refinement | 124 | 151 | Completed | Low
T0209 | P051 | E051 | CI/CD Setup - Review | 65 | 21 | In Progress | Medium
T0210 | P051 | E051 | Unit Testing - Upgrade | 113 | 0 | Not Started | Low
T0211 | P051 | E051 | Marketing Launch Prep - Testing | 193 | 0 | Not Started | High
T0212 | P051 | E051 | Compliance Documentation - Stabilization | 62 | 68 | Completed | Medium
T0213 | P052 | E016 | CI/CD Setup - Finalization | 191 | 76 | In Progress | Medium
T0214 | P052 | E016 | Requirement Gathering - Upgrade | 197 | 0 | Not Started | Medium
T0215 | P052 | E016 | Marketing Launch Prep - Module C | 40 | 17 | In Progress | Low
T0216 | P052 | E016 | Design Prototype - Compliance | 34 | 16 | In Progress | Low
T0217 | P053 | E014 | Data Migration - Phase 1 | 138 | 102 | In Progress | High
T0218 | P053 | E014 | KPI Definition - Deployment | 24 | 21 | Completed | High
T0219 | P053 | E014 | API Development - Phase 2 | 171 | 125 | In Progress | Medium
T0220 | P053 | E014 | Compliance Documentation - Module C | 125 | 92 | In Progress | Medium
T0221 | P054 | E082 | Data Migration - Review | 170 | 62 | In Progress | Low
T0222 | P054 | E017 | User Acceptance Testing - Review | 137 | 43 | In Progress | Medium
T0223 | P054 | E081 | API Development - Refinement | 95 | 43 | In Progress | Medium
T0224 | P054 | E017 | CI/CD Setup - Testing | 131 | 101 | In Progress | High
T0225 | P054 | E074 | Design Prototype - Optimization | 186 | 265 | Completed | Low
T0226 | P055 | E046 | Unit Testing - Review | 164 | 112 | In Progress | High
T0227 | P055 | E048 | API Development - Upgrade | 83 | 50 | In Progress | Medium
T0228 | P055 | E046 | Mobile App Integration - Module B | 121 | 45 | In Progress | Medium
T0229 | P055 | E048 | Design Prototype - Refinement | 99 | 80 | In Progress | Medium
T0230 | P055 | E046 | Marketing Launch Prep - Phase 1 | 144 | 65 | In Progress | High
T0231 | P056 | E034 | Compliance Documentation - Stabilization | 147 | 77 | In Progress | Medium
T0232 | P056 | E034 | CI/CD Setup - Phase 1 | 131 | 68 | In Progress | High
T0233 | P056 | E034 | Unit Testing - Validation | 128 | 116 | Completed | Medium
T0234 | P056 | E034 | Security Audit - Review | 98 | 82 | Completed | Medium
T0235 | P057 | E062 | API Development - Optimization | 199 | 60 | In Progress | High
T0236 | P057 | E052 | Security Audit - Module B | 200 | 179 | Completed | Medium
T0237 | P057 | E052 | User Acceptance Testing - Stabilization | 34 | 7 | In Progress | Medium
T0238 | P057 | E042 | Unit Testing - Module A | 64 | 44 | In Progress | Low
T0239 | P058 | E114 | Design Prototype - Integration | 93 | 0 | Not Started | High
T0240 | P058 | E095 | Mobile App Integration - Review | 53 | 0 | Not Started | Medium
T0241 | P058 | E114 | Compliance Documentation - Module B | 124 | 0 | Not Started | High
T0242 | P058 | E119 | Requirement Gathering - Module B | 79 | 0 | Not Started | Low
T0243 | P059 | E050 | Marketing Launch Prep - Review | 38 | 20 | In Progress | Medium
T0244 | P059 | E108 | User Acceptance Testing - Upgrade | 119 | 0 | Not Started | High
T0245 | P059 | E050 | Security Audit - Testing | 26 | 0 | Not Started | Medium
T0246 | P059 | E054 | KPI Definition - Phase 1 | 166 | 174 | Completed | Low
T0247 | P059 | E113 | Requirement Gathering - Review | 32 | 8 | In Progress | High
T0248 | P060 | E086 | Unit Testing - Phase 2 | 107 | 79 | In Progress | Medium
T0249 | P060 | E097 | Mobile App Integration - Initial Setup | 55 | 14 | In Progress | Low
T0250 | P060 | E097 | CI/CD Setup - Stabilization | 121 | 41 | In Progress | Medium
T0251 | P060 | E062 | Data Migration - Optimization | 167 | 75 | In Progress | Medium
T0252 | P061 | E113 | KPI Definition - Data Prep | 125 | 132 | Completed | High
T0253 | P061 | E056 | Marketing Launch Prep - Phase 1 | 88 | 47 | In Progress | High
T0254 | P061 | E035 | Mobile App Integration - Module B | 93 | 0 | Not Started | Medium
T0255 | P061 | E046 | Data Migration - Initial Setup | 109 | 67 | In Progress | Medium
T0256 | P062 | E115 | Design Prototype - Phase 2 | 185 | 81 | In Progress | High
T0257 | P062 | E069 | Mobile App Integration - Module C | 187 | 41 | In Progress | High
T0258 | P062 | E003 | KPI Definition - Optimization | 133 | 65 | In Progress | Low
T0259 | P062 | E115 | API Development - Data Prep | 63 | 35 | In Progress | Medium
T0260 | P063 | E033 | Marketing Launch Prep - Testing | 96 | 0 | Not Started | Medium
T0261 | P063 | E033 | KPI Definition - Stabilization | 103 | 0 | Not Started | Medium
T0262 | P063 | E033 | Unit Testing - Phase 1 | 80 | 0 | Not Started | Medium
T0263 | P063 | E033 | API Development - Upgrade | 90 | 10 | In Progress | Low
T0264 | P064 | E020 | Security Audit - Deployment | 84 | 49 | In Progress | Low
T0265 | P064 | E086 | API Development - Testing | 109 | 77 | In Progress | Medium
T0266 | P064 | E062 | Unit Testing - Compliance | 176 | 67 | In Progress | Low
T0267 | P064 | E025 | Design Prototype - Phase 1 | 38 | 34 | In Progress | Medium
T0268 | P065 | E083 | User Acceptance Testing - Data Prep | 110 | 106 | Completed | Low
T0269 | P065 | E083 | Security Audit - Enhancement | 94 | 66 | In Progress | Medium
T0270 | P065 | E083 | Mobile App Integration - Optimization | 29 | 38 | Completed | Medium
T0271 | P065 | E083 | CI/CD Setup - Phase 2 | 171 | 122 | In Progress | Medium
T0272 | P066 | E016 | CI/CD Setup - Testing | 135 | 166 | Completed | High
T0273 | P066 | E055 | Data Migration - Finalization | 114 | 128 | Completed | High
T0274 | P066 | E030 | API Development - Module B | 101 | 126 | Completed | Medium
T0275 | P066 | E055 | Requirement Gathering - Optimization | 144 | 153 | Completed | High
T0276 | P066 | E022 | Unit Testing - Enhancement | 67 | 50 | Completed | High
T0277 | P067 | E058 | Marketing Launch Prep - Phase 1 | 160 | 180 | Completed | Medium
T0278 | P067 | E094 | Compliance Documentation - Phase 2 | 124 | 96 | Completed | Low
T0279 | P067 | E114 | Requirement Gathering - Enhancement | 32 | 9 | In Progress | Medium
T0280 | P067 | E116 | Mobile App Integration - Review | 67 | 42 | In Progress | High
T0281 | P068 | E023 | Data Migration - Validation | 164 | 0 | Not Started | Medium
T0282 | P068 | E021 | User Acceptance Testing - Validation | 185 | 0 | Not Started | Medium
T0283 | P068 | E078 | API Development - Testing | 35 | 0 | Not Started | Medium
T0284 | P068 | E021 | Unit Testing - Stabilization | 183 | 0 | Not Started | High
T0285 | P068 | E078 | Marketing Launch Prep - Validation | 107 | 0 | Not Started | High
T0286 | P069 | E095 | Unit Testing - Phase 1 | 195 | 187 | Completed | Medium
T0287 | P069 | E095 | Requirement Gathering - Enhancement | 33 | 30 | Completed | Medium
T0288 | P069 | E095 | Mobile App Integration - Integration | 200 | 260 | Completed | High
T0289 | P069 | E095 | Data Migration - Configuration | 85 | 93 | Completed | Medium
T0290 | P070 | E114 | Mobile App Integration - Refinement | 26 | 22 | In Progress | Medium
T0291 | P070 | E102 | Requirement Gathering - Initial Setup | 62 | 61 | Completed | High
T0292 | P070 | E102 | KPI Definition - Integration | 68 | 22 | In Progress | Medium
T0293 | P070 | E065 | Security Audit - Integration | 120 | 59 | In Progress | Low
T0294 | P071 | E077 | Unit Testing - Validation | 156 | 0 | Not Started | Medium
T0295 | P071 | E038 | API Development - Phase 1 | 123 | 0 | Not Started | Medium
T0296 | P071 | E077 | User Acceptance Testing - Deployment | 38 | 4 | In Progress | High
T0297 | P071 | E077 | Design Prototype - Phase 1 | 54 | 0 | Not Started | Medium
T0298 | P071 | E077 | Mobile App Integration - Enhancement | 107 | 0 | Not Started | Low
T0299 | P072 | E028 | Data Migration - Refinement | 94 | 57 | In Progress | High
T0300 | P072 | E092 | API Development - Optimization | 32 | 0 | Not Started | Low
T0301 | P072 | E024 | Requirement Gathering - Data Prep | 147 | 65 | In Progress | High
T0302 | P072 | E091 | Marketing Launch Prep - Compliance | 34 | 30 | Completed | Low
T0303 | P069 | E095 | Unit Testing - Stabilization | 195 | 187 | Completed | Medium
T0304 | P057 | E052 | User Acceptance Testing - Module C | 34 | 7 | In Progress | Medium
T0305 | P067 | E058 | Marketing Launch Prep - Refinement | 160 | 180 | Completed | Medium
T0306 | P003 | E105 | Requirement Gathering - Module A | 122 | 127 | Completed | Medium
T0307 | P013 | E024 | Compliance Documentation - Upgrade | 121 | 56 | In Progress | Low
T0308 | P051 | E051 | CI/CD Setup - Initial Setup | 65 | 21 | In Progress | Medium
T0309 | P003 | E105 | Requirement Gathering - Optimization | 122 | 127 | Completed | Medium
T0310 | P043 | E034 | KPI Definition - Integration | 42 | 0 | Not Started | Medium
T0311 | P005 | E013 | Unit Testing - Finalization | 133 | 102 | In Progress | Medium
T0312 | P038 | E020 | Security Audit - Testing | 81 | 29 | In Progress | Low
T0313 | P072 | E024 | Requirement Gathering - Deployment | 147 | 65 | In Progress | High
T0314 | P023 | E028 | Compliance Documentation - Module C | 70 | 78 | Completed | Medium
T0315 | P036 | E098 | KPI Definition - Phase 1 | 104 | 118 | Completed | Medium
T0316 | P044 | E017 | Data Migration - Phase 1 | 44 | 17 | In Progress | High
T0317 | P004 | E006 | Compliance Documentation - Module C | 92 | 84 | Completed | High
T0318 | P015 | E015 | User Acceptance Testing - Refinement | 86 | 0 | Not Started | Medium
T0319 | P040 | E047 | Unit Testing - Module B | 155 | 102 | In Progress | High
T0320 | P068 | E078 | Marketing Launch Prep - Phase 2 | 107 | 0 | Not Started | High
T0321 | P004 | E006 | Compliance Documentation - Module C | 92 | 84 | Completed | High
T0322 | P026 | E102 | Marketing Launch Prep - Refinement | 192 | 149 | In Progress | High
T0323 | P017 | E024 | Compliance Documentation - Data Prep | 100 | 118 | Completed | Medium
T0324 | P052 | E016 | Marketing Launch Prep - Finalization | 40 | 17 | In Progress | Low
T0325 | P021 | E094 | Marketing Launch Prep - Integration | 35 | 13 | In Progress | High
T0326 | P034 | E099 | Security Audit - Review | 142 | 100 | In Progress | High
T0327 | P038 | E047 | Mobile App Integration - Optimization | 69 | 48 | In Progress | Medium
T0328 | P043 | E034 | Data Migration - Integration | 49 | 0 | Not Started | Low
T0329 | P041 | E089 | Data Migration - Refinement | 96 | 118 | Completed | High
T0330 | P060 | E097 | CI/CD Setup - Compliance | 121 | 41 | In Progress | Medium
T0331 | P033 | E027 | CI/CD Setup - Enhancement | 159 | 52 | In Progress | High
T0332 | P053 | E014 | KPI Definition - Testing | 24 | 21 | Completed | High
T0333 | P017 | E092 | CI/CD Setup - Upgrade | 130 | 74 | In Progress | Low
T0334 | P010 | E066 | Mobile App Integration - Module C | 70 | 50 | Completed | Medium
T0335 | P003 | E105 | Requirement Gathering - Compliance | 122 | 127 | Completed | Medium
T0336 | P057 | E052 | Security Audit - Review | 200 | 179 | Completed | Medium
T0337 | P011 | E047 | User Acceptance Testing - Testing | 100 | 92 | Completed | High
T0338 | P058 | E114 | Design Prototype - Phase 2 | 93 | 0 | Not Started | High
T0339 | P059 | E113 | Requirement Gathering - Initial Setup | 32 | 8 | In Progress | High
T0340 | P063 | E033 | Unit Testing - Validation | 80 | 0 | Not Started | Medium
T0341 | P038 | E047 | Mobile App Integration - Upgrade | 69 | 48 | In Progress | Medium
T0342 | P012 | E086 | Unit Testing - Data Prep | 32 | 15 | In Progress | Medium
T0343 | P066 | E030 | API Development - Initial Setup | 101 | 126 | Completed | Medium
T0344 | P063 | E033 | Unit Testing - Configuration | 80 | 0 | Not Started | Medium
T0345 | P051 | E051 | Compliance Documentation - Optimization | 62 | 68 | Completed | Medium
T0346 | P049 | E120 | Data Migration - Deployment | 85 | 51 | In Progress | Medium
T0347 | P063 | E033 | Unit Testing - Finalization | 80 | 0 | Not Started | Medium
T0348 | P062 | E003 | KPI Definition - Initial Setup | 133 | 65 | In Progress | Low
T0349 | P035 | E086 | Mobile App Integration - Finalization | 103 | 92 | Completed | High
T0350 | P014 | E030 | Marketing Launch Prep - Optimization | 196 | 0 | Not Started | Medium
T0351 | P072 | E092 | API Development - Configuration | 32 | 0 | Not Started | Low
T0352 | P043 | E034 | KPI Definition - Deployment | 42 | 0 | Not Started | Medium
T0353 | P061 | E056 | Marketing Launch Prep - Module A | 88 | 47 | In Progress | High
T0354 | P063 | E033 | Unit Testing - Initial Setup | 80 | 0 | Not Started | Medium
T0355 | P003 | E021 | Security Audit - Finalization | 142 | 182 | Completed | Medium
T0356 | P056 | E034 | CI/CD Setup - Data Prep | 131 | 68 | In Progress | High
T0357 | P057 | E052 | Security Audit - Data Prep | 200 | 179 | Completed | Medium
T0358 | P010 | E016 | Security Audit - Review | 106 | 133 | Completed | Medium
T0359 | P005 | E040 | Mobile App Integration - Module A | 162 | 71 | In Progress | High
T0360 | P051 | E051 | Marketing Launch Prep - Module A | 193 | 0 | Not Started | High
T0361 | P037 | E058 | Requirement Gathering - Review | 27 | 0 | Not Started | Medium
T0362 | P057 | E042 | Unit Testing - Validation | 64 | 44 | In Progress | Low
T0363 | P034 | E099 | Security Audit - Stabilization | 142 | 100 | In Progress | High
T0364 | P011 | E047 | User Acceptance Testing - Testing | 100 | 92 | Completed | High
T0365 | P056 | E034 | Unit Testing - Enhancement | 128 | 116 | Completed | Medium
T0366 | P057 | E042 | Unit Testing - Module C | 64 | 44 | In Progress | Low
T0367 | P018 | E030 | KPI Definition - Optimization | 83 | 66 | In Progress | Low
T0368 | P048 | E014 | Design Prototype - Integration | 168 | 70 | In Progress | High
T0369 | P029 | E087 | Design Prototype - Finalization | 78 | 25 | In Progress | High
T0370 | P045 | E018 | Compliance Documentation - Finalization | 94 | 116 | Completed | Medium
T0371 | P036 | E098 | KPI Definition - Review | 104 | 118 | Completed | Medium
T0372 | P013 | E024 | Compliance Documentation - Enhancement | 121 | 56 | In Progress | Low
T0373 | P015 | E015 | API Development - Finalization | 190 | 132 | In Progress | Low
T0374 | P002 | E101 | Mobile App Integration - Configuration | 126 | 97 | Completed | Medium
T0375 | P065 | E083 | Mobile App Integration - Phase 2 | 29 | 38 | Completed | Medium
T0376 | P034 | E099 | Mobile App Integration - Enhancement | 143 | 132 | Completed | Medium
T0377 | P071 | E077 | Design Prototype - Enhancement | 54 | 0 | Not Started | Medium
T0378 | P037 | E058 | Design Prototype - Integration | 188 | 0 | Not Started | High
T0379 | P056 | E034 | Unit Testing - Module B | 128 | 116 | Completed | Medium
T0380 | P002 | E101 | Mobile App Integration - Data Prep | 126 | 97 | Completed | Medium
T0381 | P063 | E033 | KPI Definition - Module A | 103 | 0 | Not Started | Medium
T0382 | P056 | E034 | Unit Testing - Finalization | 128 | 116 | Completed | Medium
T0383 | P069 | E095 | Data Migration - Finalization | 85 | 93 | Completed | Medium
T0384 | P071 | E077 | Mobile App Integration - Integration | 107 | 0 | Not Started | Low
T0385 | P035 | E107 | User Acceptance Testing - Refinement | 141 | 160 | Completed | Medium
T0386 | P061 | E035 | Mobile App Integration - Validation | 93 | 0 | Not Started | Medium
T0387 | P056 | E034 | Compliance Documentation - Review | 147 | 77 | In Progress | Medium
T0388 | P007 | E032 | CI/CD Setup - Phase 2 | 187 | 193 | Completed | High
T0389 | P013 | E097 | Security Audit - Optimization | 69 | 76 | Completed | Medium
T0390 | P047 | E026 | Mobile App Integration - Review | 36 | 42 | Completed | Medium
T0391 | P004 | E006 | Compliance Documentation - Module C | 92 | 84 | Completed | High
T0392 | P013 | E097 | Security Audit - Stabilization | 69 | 76 | Completed | Medium
T0393 | P009 | E083 | KPI Definition - Data Prep | 143 | 100 | Completed | Medium
T0394 | P071 | E077 | User Acceptance Testing - Enhancement | 38 | 4 | In Progress | High
T0395 | P009 | E083 | API Development - Review | 55 | 44 | Completed | High
T0396 | P016 | E030 | Design Prototype - Module B | 161 | 205 | Completed | Medium
T0397 | P043 | E034 | KPI Definition - Initial Setup | 42 | 0 | Not Started | Medium
T0398 | P002 | E101 | Mobile App Integration - Compliance | 126 | 97 | Completed | Medium
T0399 | P035 | E074 | Marketing Launch Prep - Stabilization | 132 | 133 | Completed | Medium
T0400 | P052 | E016 | Marketing Launch Prep - Phase 1 | 40 | 17 | In Progress | Low
T0401 | P067 | E058 | Marketing Launch Prep - Configuration | 160 | 180 | Completed | Medium
T0402 | P063 | E033 | Unit Testing - Review | 80 | 0 | Not Started | Medium
T0403 | P045 | E018 | Compliance Documentation - Phase 1 | 94 | 116 | Completed | Medium
T0404 | P005 | E013 | User Acceptance Testing - Integration | 101 | 0 | Not Started | High
T0405 | P058 | E119 | Requirement Gathering - Phase 1 | 79 | 0 | Not Started | Low
T0406 | P023 | E058 | CI/CD Setup - Compliance | 117 | 75 | In Progress | Medium
T0407 | P072 | E024 | Requirement Gathering - Deployment | 147 | 65 | In Progress | High
T0408 | P048 | E014 | Data Migration - Configuration | 130 | 93 | In Progress | Medium
T0409 | P051 | E051 | CI/CD Setup - Refinement | 65 | 21 | In Progress | Medium
T0410 | P045 | E018 | Compliance Documentation - Module C | 94 | 116 | Completed | Medium
T0411 | P071 | E038 | API Development - Testing | 123 | 0 | Not Started | Medium
T0412 | P043 | E034 | KPI Definition - Configuration | 42 | 0 | Not Started | Medium
T0413 | P048 | E014 | Security Audit - Module B | 158 | 164 | Completed | High
T0414 | P018 | E030 | API Development - Upgrade | 145 | 49 | In Progress | High
T0415 | P040 | E047 | Unit Testing - Enhancement | 155 | 102 | In Progress | High
T0416 | P008 | E111 | KPI Definition - Module C | 50 | 41 | Completed | High
T0417 | P027 | E116 | CI/CD Setup - Enhancement | 115 | 53 | In Progress | High
T0418 | P065 | E083 | Mobile App Integration - Data Prep | 29 | 38 | Completed | Medium
T0419 | P061 | E046 | Data Migration - Upgrade | 109 | 67 | In Progress | Medium
T0420 | P069 | E095 | Mobile App Integration - Enhancement | 200 | 260 | Completed | High
T0421 | P005 | E013 | Unit Testing - Configuration | 133 | 102 | In Progress | Medium
T0422 | P057 | E052 | User Acceptance Testing - Configuration | 34 | 7 | In Progress | Medium
T0423 | P002 | E078 | Data Migration - Review | 68 | 64 | Completed | High
T0424 | P062 | E115 | Design Prototype - Compliance | 185 | 81 | In Progress | High
T0425 | P001 | E112 | User Acceptance Testing - Validation | 184 | 211 | Completed | High
T0426 | P022 | E012 | Data Migration - Phase 2 | 25 | 19 | In Progress | High
T0427 | P032 | E083 | Design Prototype - Integration | 89 | 66 | In Progress | High
T0428 | P018 | E030 | KPI Definition - Optimization | 83 | 66 | In Progress | Low
T0429 | P057 | E052 | Security Audit - Enhancement | 200 | 179 | Completed | Medium
T0430 | P056 | E034 | Unit Testing - Phase 1 | 128 | 116 | Completed | Medium
T0431 | P029 | E087 | CI/CD Setup - Optimization | 91 | 89 | Completed | Medium
T0432 | P044 | E017 | Data Migration - Refinement | 44 | 17 | In Progress | High
T0433 | P015 | E015 | API Development - Compliance | 190 | 132 | In Progress | Low
T0434 | P016 | E076 | CI/CD Setup - Deployment | 107 | 152 | Completed | High
T0435 | P037 | E058 | Requirement Gathering - Stabilization | 27 | 0 | Not Started | Medium
T0436 | P009 | E083 | Requirement Gathering - Review | 40 | 18 | In Progress | Medium
T0437 | P059 | E050 | Security Audit - Upgrade | 26 | 0 | Not Started | Medium
T0438 | P054 | E074 | Design Prototype - Module B | 186 | 265 | Completed | Low
T0439 | P036 | E098 | Requirement Gathering - Stabilization | 163 | 101 | In Progress | High
T0440 | P053 | E014 | API Development - Module A | 171 | 125 | In Progress | Medium
T0441 | P056 | E034 | Unit Testing - Testing | 128 | 116 | Completed | Medium
T0442 | P046 | E057 | KPI Definition - Enhancement | 198 | 65 | In Progress | Medium
T0443 | P049 | E120 | Data Migration - Refinement | 85 | 51 | In Progress | Medium
T0444 | P053 | E014 | API Development - Validation | 171 | 125 | In Progress | Medium
T0445 | P012 | E051 | API Development - Module C | 196 | 73 | In Progress | Medium
T0446 | P052 | E016 | Requirement Gathering - Module B | 197 | 0 | Not Started | Medium
T0447 | P046 | E086 | Data Migration - Integration | 47 | 0 | Not Started | High
T0448 | P013 | E024 | Compliance Documentation - Finalization | 121 | 56 | In Progress | Low
T0449 | P040 | E047 | Unit Testing - Stabilization | 155 | 102 | In Progress | High
T0450 | P061 | E035 | Mobile App Integration - Module B | 93 | 0 | Not Started | Medium
T0451 | P054 | E074 | Design Prototype - Finalization | 186 | 265 | Completed | Low
T0452 | P041 | E003 | CI/CD Setup - Deployment | 168 | 131 | In Progress | Medium
T0453 | P059 | E050 | Marketing Launch Prep - Integration | 38 | 20 | In Progress | Medium
T0454 | P049 | E012 | Mobile App Integration - Initial Setup | 110 | 64 | In Progress | High
T0455 | P042 | E106 | CI/CD Setup - Module A | 44 | 48 | Completed | Low
T0456 | P043 | E034 | Data Migration - Integration | 49 | 0 | Not Started | Low
T0457 | P029 | E056 | Unit Testing - Enhancement | 70 | 15 | In Progress | Medium
T0458 | P028 | E097 | CI/CD Setup - Configuration | 104 | 51 | In Progress | Medium
T0459 | P049 | E012 | Mobile App Integration - Stabilization | 110 | 64 | In Progress | High
T0460 | P053 | E014 | Data Migration - Upgrade | 138 | 102 | In Progress | High
T0461 | P002 | E101 | Mobile App Integration - Refinement | 126 | 97 | Completed | Medium
T0462 | P042 | E002 | Marketing Launch Prep - Phase 1 | 78 | 91 | Completed | Medium
T0463 | P003 | E078 | Mobile App Integration - Testing | 47 | 43 | Completed | Medium
T0464 | P058 | E114 | Design Prototype - Deployment | 93 | 0 | Not Started | High
T0465 | P071 | E077 | Mobile App Integration - Module B | 107 | 0 | Not Started | Low
T0466 | P035 | E086 | Mobile App Integration - Phase 2 | 103 | 92 | Completed | High
T0467 | P044 | E017 | Data Migration - Compliance | 44 | 17 | In Progress | High
T0468 | P028 | E062 | API Development - Validation | 51 | 46 | Completed | Medium
T0469 | P068 | E078 | API Development - Data Prep | 35 | 0 | Not Started | Medium
T0470 | P044 | E105 | Design Prototype - Refinement | 119 | 51 | In Progress | Medium
T0471 | P045 | E018 | CI/CD Setup - Upgrade | 137 | 99 | In Progress | Low
T0472 | P061 | E113 | KPI Definition - Refinement | 125 | 132 | Completed | High
T0473 | P026 | E102 | API Development - Data Prep | 188 | 143 | In Progress | Medium
T0474 | P071 | E077 | Design Prototype - Initial Setup | 54 | 0 | Not Started | Medium
T0475 | P023 | E058 | CI/CD Setup - Stabilization | 117 | 75 | In Progress | Medium
T0476 | P063 | E033 | Unit Testing - Phase 2 | 80 | 0 | Not Started | Medium
T0477 | P044 | E017 | Data Migration - Module A | 44 | 17 | In Progress | High
T0478 | P018 | E030 | KPI Definition - Module C | 83 | 66 | In Progress | Low
T0479 | P067 | E058 | Marketing Launch Prep - Finalization | 160 | 180 | Completed | Medium
T0480 | P003 | E105 | Requirement Gathering - Initial Setup | 122 | 127 | Completed | Medium
T0481 | P017 | E024 | Compliance Documentation - Module B | 100 | 118 | Completed | Medium
T0482 | P005 | E013 | Unit Testing - Module B | 133 | 102 | In Progress | Medium
T0483 | P058 | E114 | Design Prototype - Module B | 93 | 0 | Not Started | High
T0484 | P041 | E089 | Data Migration - Module C | 96 | 118 | Completed | High
T0485 | P069 | E095 | Unit Testing - Compliance | 195 | 187 | Completed | Medium
T0486 | P066 | E022 | Unit Testing - Module B | 67 | 50 | Completed | High
T0487 | P057 | E052 | Security Audit - Data Prep | 200 | 179 | Completed | Medium
T0488 | P045 | E018 | Marketing Launch Prep - Finalization | 46 | 61 | Completed | Medium
T0489 | P034 | E099 | KPI Definition - Configuration | 108 | 129 | Completed | Low
T0490 | P036 | E098 | KPI Definition - Refinement | 104 | 118 | Completed | Medium
T0491 | P002 | E078 | Data Migration - Review | 68 | 64 | Completed | High
T0492 | P048 | E014 | Design Prototype - Optimization | 168 | 70 | In Progress | High
T0493 | P003 | E078 | Mobile App Integration - Compliance | 47 | 43 | Completed | Medium
T0494 | P071 | E077 | Design Prototype - Testing | 54 | 0 | Not Started | Medium
T0495 | P043 | E034 | KPI Definition - Refinement | 42 | 0 | Not Started | Medium
T0496 | P035 | E107 | User Acceptance Testing - Validation | 141 | 160 | Completed | Medium
T0497 | P013 | E024 | Compliance Documentation - Module A | 121 | 56 | In Progress | Low
T0498 | P015 | E015 | API Development - Configuration | 190 | 132 | In Progress | Low
T0499 | P046 | E025 | Compliance Documentation - Upgrade | 51 | 32 | In Progress | Medium
T0500 | P028 | E097 | CI/CD Setup - Stabilization | 104 | 51 | In Progress | Medium
T0501 | P022 | E077 | Mobile App Integration - Module B | 184 | 60 | In Progress | Medium
T0502 | P060 | E097 | CI/CD Setup - Configuration | 121 | 41 | In Progress | Medium
T0503 | P052 | E016 | Marketing Launch Prep - Finalization | 40 | 17 | In Progress | Low
T0504 | P038 | E047 | Mobile App Integration - Optimization | 69 | 48 | In Progress | Medium
T0505 | P009 | E083 | Requirement Gathering - Configuration | 40 | 18 | In Progress | Medium
T0506 | P015 | E050 | Security Audit - Deployment | 192 | 109 | In Progress | Medium
T0507 | P019 | E104 | Unit Testing - Deployment | 131 | 121 | Completed | Medium
T0508 | P034 | E099 | KPI Definition - Deployment | 108 | 129 | Completed | Low
T0509 | P004 | E055 | KPI Definition - Phase 2 | 30 | 34 | Completed | Medium
T0510 | P044 | E105 | Design Prototype - Optimization | 119 | 51 | In Progress | Medium
T0511 | P066 | E022 | Unit Testing - Initial Setup | 67 | 50 | Completed | High
T0512 | P017 | E092 | CI/CD Setup - Phase 2 | 130 | 74 | In Progress | Low
T0513 | P052 | E016 | Design Prototype - Refinement | 34 | 16 | In Progress | Low
T0514 | P072 | E024 | Requirement Gathering - Compliance | 147 | 65 | In Progress | High
T0515 | P041 | E003 | CI/CD Setup - Deployment | 168 | 131 | In Progress | Medium
T0516 | P028 | E062 | API Development - Optimization | 51 | 46 | Completed | Medium
T0517 | P039 | E074 | API Development - Testing | 54 | 37 | In Progress | Low
T0518 | P039 | E074 | Compliance Documentation - Phase 1 | 152 | 199 | Completed | High
T0519 | P036 | E098 | Data Migration - Review | 183 | 232 | Completed | High
T0520 | P029 | E087 | Design Prototype - Deployment | 78 | 25 | In Progress | High
T0521 | P041 | E089 | Data Migration - Integration | 96 | 118 | Completed | High
T0522 | P034 | E099 | Security Audit - Optimization | 142 | 100 | In Progress | High
T0523 | P058 | E095 | Mobile App Integration - Phase 2 | 53 | 0 | Not Started | Medium
T0524 | P051 | E051 | CI/CD Setup - Stabilization | 65 | 21 | In Progress | Medium
T0525 | P053 | E014 | API Development - Optimization | 171 | 125 | In Progress | Medium
T0526 | P023 | E023 | API Development - Phase 1 | 115 | 55 | In Progress | Medium
T0527 | P004 | E107 | API Development - Module A | 177 | 202 | Completed | High
T0528 | P009 | E083 | Requirement Gathering - Enhancement | 40 | 18 | In Progress | Medium
T0529 | P051 | E051 | Compliance Documentation - Testing | 62 | 68 | Completed | Medium
T0530 | P068 | E078 | API Development - Optimization | 35 | 0 | Not Started | Medium
T0531 | P037 | E058 | Data Migration - Deployment | 190 | 0 | Not Started | Medium
T0532 | P035 | E086 | Mobile App Integration - Module A | 103 | 92 | Completed | High
T0533 | P068 | E078 | API Development - Stabilization | 35 | 0 | Not Started | Medium
T0534 | P047 | E018 | API Development - Enhancement | 196 | 241 | Completed | Low
T0535 | P010 | E016 | Security Audit - Stabilization | 106 | 133 | Completed | Medium
T0536 | P060 | E097 | CI/CD Setup - Finalization | 121 | 41 | In Progress | Medium
T0537 | P041 | E003 | CI/CD Setup - Initial Setup | 168 | 131 | In Progress | Medium
T0538 | P070 | E065 | Security Audit - Configuration | 120 | 59 | In Progress | Low
T0539 | P014 | E087 | Requirement Gathering - Module A | 75 | 0 | Not Started | Low
T0540 | P057 | E052 | User Acceptance Testing - Initial Setup | 34 | 7 | In Progress | Medium
T0541 | P056 | E034 | Unit Testing - Module A | 128 | 116 | Completed | Medium
T0542 | P043 | E034 | KPI Definition - Deployment | 42 | 0 | Not Started | Medium
T0543 | P033 | E027 | CI/CD Setup - Deployment | 159 | 52 | In Progress | High
T0544 | P046 | E086 | Data Migration - Finalization | 47 | 0 | Not Started | High
T0545 | P017 | E092 | CI/CD Setup - Configuration | 130 | 74 | In Progress | Low
T0546 | P040 | E047 | Unit Testing - Stabilization | 155 | 102 | In Progress | High
T0547 | P005 | E013 | Unit Testing - Validation | 133 | 102 | In Progress | Medium
T0548 | P069 | E095 | Data Migration - Optimization | 85 | 93 | Completed | Medium
T0549 | P043 | E034 | KPI Definition - Testing | 42 | 0 | Not Started | Medium
T0550 | P037 | E058 | Requirement Gathering - Upgrade | 27 | 0 | Not Started | Medium
T0551 | P007 | E032 | CI/CD Setup - Data Prep | 187 | 193 | Completed | High
T0552 | P006 | E090 | Compliance Documentation - Refinement | 38 | 8 | In Progress | Medium
T0553 | P056 | E034 | Unit Testing - Enhancement | 128 | 116 | Completed | Medium
T0554 | P015 | E015 | API Development - Configuration | 190 | 132 | In Progress | Low
T0555 | P063 | E033 | KPI Definition - Phase 1 | 103 | 0 | Not Started | Medium
T0556 | P068 | E078 | API Development - Module C | 35 | 0 | Not Started | Medium
T0557 | P055 | E046 | Marketing Launch Prep - Module A | 144 | 65 | In Progress | High
T0558 | P005 | E013 | User Acceptance Testing - Enhancement | 101 | 0 | Not Started | High
T0559 | P036 | E098 | Requirement Gathering - Integration | 163 | 101 | In Progress | High
T0560 | P038 | E047 | Marketing Launch Prep - Module A | 144 | 141 | Completed | Medium
T0561 | P003 | E078 | Mobile App Integration - Validation | 47 | 43 | Completed | Medium
T0562 | P057 | E052 | User Acceptance Testing - Finalization | 34 | 7 | In Progress | Medium
T0563 | P029 | E087 | Design Prototype - Module B | 78 | 25 | In Progress | High
T0564 | P013 | E097 | Security Audit - Testing | 69 | 76 | Completed | Medium
T0565 | P060 | E086 | Unit Testing - Module B | 107 | 79 | In Progress | Medium
T0566 | P046 | E057 | KPI Definition - Configuration | 198 | 65 | In Progress | Medium
T0567 | P023 | E090 | Data Migration - Validation | 86 | 86 | Completed | Medium
T0568 | P054 | E017 | CI/CD Setup - Initial Setup | 131 | 101 | In Progress | High
T0569 | P055 | E046 | Marketing Launch Prep - Optimization | 144 | 65 | In Progress | High
T0570 | P060 | E062 | Data Migration - Upgrade | 167 | 75 | In Progress | Medium
T0571 | P011 | E047 | User Acceptance Testing - Module B | 100 | 92 | Completed | High
T0572 | P028 | E097 | CI/CD Setup - Stabilization | 104 | 51 | In Progress | Medium
T0573 | P034 | E099 | KPI Definition - Configuration | 108 | 129 | Completed | Low
T0574 | P035 | E086 | Compliance Documentation - Module B | 169 | 70 | In Progress | High
T0575 | P034 | E099 | Security Audit - Testing | 142 | 100 | In Progress | High
T0576 | P009 | E083 | KPI Definition - Stabilization | 143 | 100 | Completed | Medium
T0577 | P009 | E083 | Requirement Gathering - Module B | 40 | 18 | In Progress | Medium
T0578 | P071 | E077 | Design Prototype - Phase 2 | 54 | 0 | Not Started | Medium
T0579 | P018 | E030 | KPI Definition - Finalization | 83 | 66 | In Progress | Low
T0580 | P046 | E086 | Data Migration - Refinement | 47 | 0 | Not Started | High
T0581 | P061 | E056 | Marketing Launch Prep - Optimization | 88 | 47 | In Progress | High
T0582 | P062 | E003 | KPI Definition - Phase 1 | 133 | 65 | In Progress | Low
T0583 | P015 | E050 | Security Audit - Optimization | 192 | 109 | In Progress | Medium
T0584 | P014 | E055 | Mobile App Integration - Data Prep | 87 | 103 | Completed | Medium
T0585 | P022 | E036 | Security Audit - Initial Setup | 90 | 40 | In Progress | Medium
T0586 | P056 | E034 | Compliance Documentation - Review | 147 | 77 | In Progress | Medium
T0587 | P057 | E052 | Security Audit - Validation | 200 | 179 | Completed | Medium
T0588 | P065 | E083 | Mobile App Integration - Initial Setup | 29 | 38 | Completed | Medium
T0589 | P002 | E101 | Mobile App Integration - Optimization | 126 | 97 | Completed | Medium
T0590 | P059 | E050 | Security Audit - Optimization | 26 | 0 | Not Started | Medium
T0591 | P046 | E086 | Data Migration - Enhancement | 47 | 0 | Not Started | High
T0592 | P021 | E036 | CI/CD Setup - Module B | 94 | 76 | Completed | Medium
T0593 | P048 | E014 | Security Audit - Module A | 158 | 164 | Completed | High
T0594 | P062 | E115 | Design Prototype - Deployment | 185 | 81 | In Progress | High
T0595 | P034 | E099 | Mobile App Integration - Testing | 143 | 132 | Completed | Medium
T0596 | P071 | E077 | Design Prototype - Stabilization | 54 | 0 | Not Started | Medium
T0597 | P013 | E024 | Compliance Documentation - Initial Setup | 121 | 56 | In Progress | Low
T0598 | P056 | E034 | Unit Testing - Module B | 128 | 116 | Completed | Medium
T0599 | P039 | E074 | KPI Definition - Testing | 117 | 52 | In Progress | Medium
T0600 | P038 | E047 | Mobile App Integration - Data Prep | 69 | 48 | In Progress | Medium
T0601 | P048 | E014 | Security Audit - Configuration | 158 | 164 | Completed | High
T0602 | P012 | E062 | Design Prototype - Stabilization | 113 | 79 | In Progress | Medium
T0603 | P049 | E120 | Data Migration - Data Prep | 85 | 51 | In Progress | Medium
T0604 | P035 | E074 | Marketing Launch Prep - Deployment | 132 | 133 | Completed | Medium
T0605 | P011 | E047 | KPI Definition - Phase 2 | 197 | 129 | In Progress | Low
T0606 | P005 | E013 | User Acceptance Testing - Configuration | 101 | 0 | Not Started | High
T0607 | P010 | E066 | Data Migration - Compliance | 136 | 148 | Completed | Medium
T0608 | P009 | E083 | API Development - Integration | 55 | 44 | Completed | High
T0609 | P009 | E083 | Requirement Gathering - Optimization | 40 | 18 | In Progress | Medium
T0610 | P058 | E095 | Mobile App Integration - Phase 2 | 53 | 0 | Not Started | Medium
T0611 | P072 | E024 | Requirement Gathering - Refinement | 147 | 65 | In Progress | High
T0612 | P002 | E101 | Mobile App Integration - Data Prep | 126 | 97 | Completed | Medium
T0613 | P033 | E027 | Marketing Launch Prep - Initial Setup | 200 | 207 | Completed | High
T0614 | P054 | E081 | API Development - Phase 2 | 95 | 43 | In Progress | Medium
T0615 | P051 | E051 | Marketing Launch Prep - Optimization | 193 | 0 | Not Started | High
T0616 | P047 | E026 | Mobile App Integration - Module C | 36 | 42 | Completed | Medium
T0617 | P056 | E034 | Unit Testing - Deployment | 128 | 116 | Completed | Medium
T0618 | P066 | E022 | Unit Testing - Configuration | 67 | 50 | Completed | High
T0619 | P010 | E016 | Security Audit - Module B | 106 | 133 | Completed | Medium
T0620 | P023 | E028 | Compliance Documentation - Configuration | 70 | 78 | Completed | Medium
T0621 | P009 | E083 | Requirement Gathering - Module A | 40 | 18 | In Progress | Medium
T0622 | P061 | E056 | Marketing Launch Prep - Stabilization | 88 | 47 | In Progress | High
T0623 | P025 | E087 | Security Audit - Upgrade | 98 | 67 | In Progress | Medium
T0624 | P065 | E083 | User Acceptance Testing - Module B | 110 | 106 | Completed | Low